## Slide 1: Improving Dual Diagnosis Services: Report to the ESVG Board
February 25th 2015
Conrad Eydmann – Head of substance misuse strategy and delivery
Louise Poley – Consultant Nurse Substance Misuse
Jill Hawkins – Community Mental Health CPN, & Project Lead Officer

## Slide 2: CONTENTS
BACKGROUND AND INTRODUCTION
IMPLEMENTATION
DELIVERY – LINK WORKERS
DELIVERY – TRAINING
DELIVERY – COHORT STUDY
KEY FINDINGS & LEARNING – STRATEGIC
KEY FINDINGS & LEARNING – OPERATIONAL
RECOMMENDATIONS

## Slide 3: BACKGROUND AND INTRODUCTION
National difficulties in delivering the service framework – X3 iterations
Local pathway and protocols drawn up
Involvement of the ESVG
Assumption that delivering services across disciplines for complex needs would be transferable
Multi-agency approach

## Slide 4: Implementation
Substance misuse led – contrary to national guidance
APB sponsorship with a line of sight into LMHPB
Multi-agency steering group
Identification of support budget and appointment of project lead
Three strand approach – Training, link workers and cohort study

## Slide 5: Delivery 1: Link Workers
Role descriptor agreed
Training delivered – evidence based, manualised interventions
Regular supervision and joint meetings introduced

## Slide 6: Delivery 2: Training
Multi agency, multi professional training, service user involvement
MI /Manualised interventions CBT stimulants, cannabis and MET alcohol
CBT anxiety
Planning – Modular Dual Diagnosis programme including specific Personality Disorder training

## Slide 7: Delivery 3: Cohort study
Cohorts identified according to Minkoffs model
Baseline data collected – TOPS, HoNOS
Minimal effect noted during pilot period
Multi faceted challenges

## Slide 8: Key findings and learning: Operational
Senior management participation required at inception
Clinical leadership vital
Sustained training and supervision key to effective implementation – challenges of competing priorities, releasing staff etc
Drive to engage and retain organisations in partnership working required – champions identification

## Slide 9: Key findings and learning: Strategic
Multi-agency working difficulties can’t be resolved until internal relationships have been addressed
Skills mix in services can be improved to make best use of qualified specialist staff time
The services that identify individuals may not be best placed to meet their needs, but need to prioritise reduced disengagement
Senior management support is critical to success, and the only means of addressing cross-discipline difficulties
Training needs to be undertaken at a whole systems level – from non-specialist staff through to those wanting to champion a specific issue within their services

## Slide 10: RECOMMENDATIONS
Piloting system navigators
Developing a structured tiered approach to training
Ensuring that interdisciplinary working arrangements within health services are robust enough for external agencies to have a clear line of sight into the organisation
Establishing effective identification and retention systems for high risk individuals in contact with low threshold services