## Cover
Programme Business Case
Health Board/Trust: |  | All Wales WHSSC
Hospital/Site | : | Various
Project Title | : | All Wales PET CT Programme
Project No | :
Option No | : | 4
Option Title | : | Cardiff plus 4 PET sites
Prepared by | : | NWSSP SES / WHSSC
Date | : | 2021-03-01

## PBC1
___________________________________________________________________________________________________
Project Title |  | All Wales PET CT Programme
Option No |  | 4
Option Title |  | Cardiff plus 4 PET sites
_______________________________________________________________________________________
BASIS OF ESTIMATING
Healthcare Capital Investment document Version 2
BIS PUBSEC Index Level FP/VP |  |  | : | ***
Equipment cost level |  |  | : | ***
Location factor |  |  | : | 0.97
Proposed start on site |  |  | : | 2022-04-01
[10 empty] | 21/22 | 22/23 | 23/24 | 24/25 | 25/26 | 26/27 | 27/28 | 28/29
Proposed completion date |  |  | : | 2026-03-01 |  |  |  |  | Cardiff | 21/22: BJC; 22/23: Installation
[9 empty] | Swansea | 21/22: OBC; 22/23: FBC; 23/24: Installation
Capital Cost Summary | [8 empty] | N Wales | 21/22: OBC; 22/23: FBC; 23/24: Installation
[9 empty] | 4th Facility | 23/24: OBC; 24/25: FBC; 25/26: Installation
Ref | Cost Centre |  |  |  | Net | VAT | Gross |  | 5th Facility | 26/27: OBC; 27/28: FBC; 28/29: Installation
[5 empty] | £ | £ | £ |  |  | 21/22 | 22/23 | 23/24 | 24/25 | 25/26 | 26/27 | 27/28 | 28/29 | Total
1 | Departmental Cost (PBC2) |  |  |  | 4697000 | 939400 | 5636400 |  |  | 0 | 45000 | 2062000 |  | 1295000 |  |  | 1295000 | 4697000 | 4 sites only - cardiff £0
2 | Oncosts (PBC3) |  | 35% |  | 1643950 | 328790 | 1972740 |  |  | 0 | 15750 | 721700 | 0 | 453250 | 0 | 0 | 453250 | 1643950 | 4 sites only - cardiff £0
3 | Sub-total |  |  |  | 6340950 | 1268190 | 7609140
4 | Provisional location adjustment |  |  | 100% | 0 | 0 | 0
5 | Works Cost |  |  |  | 6340950 | 1268190 | 7609140 |  |  | 0 | 60750 | 2783700 | 0 | 1748250 | 0 | 0 | 1748250 | 6340950 | 4 sites only - cardiff £0
6 | Fees (PBC4) |  | 16% |  | 1014552 | 202910.4 | 1217462.4 |  |  | 139449.6 | 182044.8 | 217533.6 | 111888 | 83916 | 83916 | 111888 | 83916 | 1014552 | 4 sites only - cardiff £0
7 | Non-works Costs (PBC4) |  |  |  | 120000 | 24000 | 144000 |  |  | 20000 | 30000 | 10000 | 20000 | 10000 |  | 20000 | 10000 | 120000 | Surveys
8 | Equipment Costs (PBC2) |  | (**% of (1) |  | 16513000 | 3302600 | 19815600 |  |  | 3413000 | 1300000 | 5880000 |  | 2960000 |  |  | 2960000 | 16513000 | split cardiff from 3 other sites
9 | Planning Contingency |  | 10% |  | 2398850.2 | 479770.04 | 2878620.24 | 23988502 |  | 357244.96 | 157279.48 | 889123.36 | 13188.8 | 480216.6 | 8391.6 | 13188.8 | 480216.6 | 2398850.2 | 10%
10 | Forecast Project Out-turn Cost (Pre VAT Recovery) |  |  |  | 26387352.2 | 5277470.44 | 31664822.64 |  |  | 3929694.56 | 1730074.28 | 9780356.96 | 145076.8 | 5282382.6 | 92307.6 | 145076.8 | 5282382.6 | 26387352.2
11 | LESS Recoverable VAT (PBC7) |  |  | inc |  | -202910.4 | -202910.4 |  | VAT 20% | 785938.912 | 346014.856 | 1956071.392 | 29015.36 | 1056476.52 | 18461.52 | 29015.36 | 1056476.52 | 5277470.44
[9 empty] | Vat reclaim | 27889.92 | 36408.96 | 43506.72 | 22377.6 | 16783.2 | 16783.2 | 22377.6 | 16783.2 | 202910.4
12 | Project Cost (1Q2021) |  |  |  | 26387352.2 | 5074560.04 | 31461912.24 |  |  | 4687743.552 | 2039680.176 | 11692921.632 | 151714.56 | 6322075.92 | 93985.92 | 151714.56 | 6322079.92 | 31461912.24
13 | Project Cost (Reporting PUBSEC 250)

## PBC2
___________________________________________________________________________________________________
Project Title |  | All Wales PET CT Programme
Option No |  | 4
Option Title |  | Cardiff plus 4 PET sites
___________________________________________________________________________________________________
CAPITAL COSTS: DEPARTMENTAL AND EQUIPMENT COSTS
Accommodation |  |  | Functional Size | Space allowance |  | N/A/C | Departmental | Equipment
(Assessment of Projects within Programme) | [6 empty] | Allowance | Allowance
|  |  |  | m2 | £/m2 |  | £ | £
Cardiff | Hot cell build works | [5 empty] | 45000
| PET Scanner | [6 empty] | 2500000
| Ancillary Equipment | [6 empty] | 300000
| Radiotherapy adaptions | [6 empty] | 120000
| Cyclotron |  | Ion source replacement |  |  |  |  | 453000
|  |  | Hot cells replacement |  |  |  |  | 1300000 | 4673000
Swansea | New build |  |  | 40 | 4000 |  | 160000
| Refurbish existing |  |  | 176 | 2000 | A | 352000
| Lead Lining |  | £232K+10% |  |  |  | 255000
| PET Scanner | [6 empty] | 2500000
| Ancillary Equipment | [6 empty] | 300000
| Radiotherapy adaptions | [6 empty] | 120000
2920000
N Wales
| New build |  |  | 260 | 4000 | N | 1040000
| Lead Lining |  | £232K+10% |  |  |  | 255000
| PET Scanner | [6 empty] | 2500000
| Ancillary Equipment | [6 empty] | 300000
| Radiotherapy adaptions | [6 empty] | 120000
2920000
4th Facility (TBA)
| New build |  |  | 260 | 4000 | N | 1040000
| Lead Lining |  | £232K+10% |  |  |  | 255000
| PET Scanner | [6 empty] | 2500000 |  | 25/26
| Ancillary Equipment | [6 empty] | 300000
| Radiotherapy adaptions | [6 empty] | 120000
2920000
5th Facility (TBA)
| New build |  |  | 260 | 4000 | N | 1040000
| Lead Lining |  | £232K+10% |  |  |  | 255000
| PET Scanner | [6 empty] | 2500000 |  | 28/29
| Ancillary Equipment | [6 empty] | 300000
| Radiotherapy adaptions | [6 empty] | 120000
2920000
Loose equipment (4 sites) | [7 empty] | 160000
40000
40000
40000
40000
|  |  | Total floor area | 996 | m2
16513000
Less: Abatement for transferred equipment 0 % | [7 empty] | 0
16513000
|  | Departmental Cost - to PBC1 Summary |  |  |  |  | 4697000
|  |  |  | Equipment Cost - to PBC1 Summary |  |  |  | 16513000

## PBC3
_________________________________________________________________________
Project Title |  | All Wales PET CT Programme
Option No |  | 4
Option Title |  | Cardiff plus 4 PET sites
_________________________________________________________________________
CAPITAL COSTS: ON-COSTS
|  |  |  | Net | % of
|  |  |  | Cost | DCA
1 | Communications |  | )
| a | Space | ) | See PBC1
| b | Medical Gases | )
| c | Lifts | )
)
2 | "External" Building Work |  | )
| a | Drainage | )
| b | Roads, paths, parking | )
| c | Site layout, walls, fencing, gates | )
| d | BWIC with "External" engineering work | )
)
3 | "External" Engineering Work |  | )
| a | Steam, condensate, heating, hot water | )
|  | and gas supply mains | )
| b | Cold water mains and storage | )
| c | Electricity mains, sub-stations, | )
|  | standby generating plant | )
| d | Calorifiers and associated plant | )
| e | Miscellaneous services | )
)
4 | Auxilliary Buildings |  | )
)
5 | Other on-costs and abnormals |  | )
| a | Building abnormals(See Annex A) | )
| b | Engineering(See Annex B) | )
| c | Other on-costs(See Annex C) | )
)
|  | Total On-costs - to SOC1 Summary |  | 0 | 0%

## PBC4
_________________________________________________________________________
Project Title |  | All Wales PET CT Programme
Option No |  | 4
Option Title |  | Cardiff plus 4 PET sites
_________________________________________________________________________
CAPITAL COSTS: FEES AND NON-WORKS COSTS
% of Works
|  |  | £ | Cost
1 | Fees |  | 6340950
HB/Trust
| a. Project Manager |  | 158523.75 | 2.5%
| b. Trust Cost Advisor |  | Inc
| c. Supervisor |  | Inc
| d. Host organisation Programme Management and Admin support |  | 158523.75 | 2.5%
| e. In-house Project Sponsorship |  | Inc
| f. Financial Vetting |  | Inc
| g. Audit |  | Inc
| h. Specialist Advisors |  | 63409.5 | 1%
SCP / Constructor
| j. Constructor - pre-construction |  | 0
| k. Project Manager |  | 0
| l. Health Planner |  | 0
| m. Architect |  | 634095 | 10%
| n. Civil and Structural Engineer |  | Inc
| o. Building Services Engineer |  | Inc
| p. Planning Supervisor |  | Inc
| q. Cost Manager |  | Inc
| r. FM Advisor |  | Inc
| s. Building Services Installer- pre-construction |  | Inc
| t. Other |  | 0
|  | Total Fees to SOC1 Summary | 1014552 | 16%
2 | Non-Works Costs
a. Land purchase costs and associated legal fees
|  | Assumed all NHS land | 0
b. Statutory and Local Authority charges
| c. Planning and Building Control fees |  | 40000
| d. Survey Fees |  | 50000
| d. Other |  | 30000
|  | Total Non-Works Costs to PBC1 Summary | 120000

## PBC5
_________________________________________________________________________
Project Title |  | All Wales PET CT Programme
Option No |  | 4
Option Title |  | Cardiff plus 4 PET sites
_________________________________________________________________________
PROJECT CASHFLOW FORECAST
Proposed start on site:
Proposed completion date:
| Year | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 6 | Total
| Financial year | 2021/2022 | 2022/2023 | 2023/2024 | 2024/2025 | 2025/2026 | 2026/2027 | 2027/2028 | 2027/2028
| Works Cost | 0 | 60750 | 2783700 | 0 | 1748250 | 0 | 0 | 1748250 | 6340950
| Fees | 139449.6 | 182044.8 | 217533.6 | 111888 | 83916 | 83916 | 111888 | 83916 | 1014552
| Non-works Costs | 20000 | 30000 | 10000 | 20000 | 10000 | 0 | 20000 | 10000 | 120000
| Equipment Costs | 3413000 | 1300000 | 5880000 | 0 | 2960000 | 0 | 0 | 2960000 | 16513000
| Quantified Risk/Contingency | 357244.96 | 157279.48 | 889123.36 | 13188.8 | 480216.6 | 8391.6 | 13188.8 | 480216.6 | 2398850.2
| Sub-total | 3929694.56 | 1730074.28 | 9780356.96 | 145076.8 | 5282382.6 | 92307.6 | 145076.8 | 5282382.6 | 26387352.2
0
| Gross VAT | 785938.912 | 346014.856 | 1956071.392 | 29015.36 | 1056476.52 | 18461.52 | 29015.36 | 1056476.52 | 5277470.44
| Less: Reclaimable VAT | 27889.92 | 36408.96 | 43506.72 | 22377.6 | 16783.2 | 16783.2 | 22377.6 | 16783.2 | 202910.4
| Net VAT | 758048.992 | 309605.896 | 1912564.672 | 6637.76 | 1039693.32 | 1678.32 | 6637.76 | 1039693.32 | 5074560.04
| Total | 4687743.552 | 2039680.176 | 11692921.632 | 151714.56 | 6322075.92 | 93985.92 | 151714.56 | 6322079.92 | 31461912.24

## PBC6
_________________________________________________________________________
Project Title |  | All Wales PET CT Programme
Option No |  | 4
Option Title |  | Cardiff plus 4 PET sites
_________________________________________________________________________
CASHFLOW FORECAST OF FUNDING SOURCES
TO BE COMPLETED IF THERE ARE OTHER FUNDING SOURCES PROPOSED OTHER THAN WG NHS CAPITAL
Proposed start on site:
Proposed completion date:
Funding source: Department for Health and Social Services: Welsh Assembly Government
| Year | 0 | 1 | 2 | 3 | 4 | 5 | 6 | Total
| Financial year | 2021/2022 | 2022/2023 | 2023/2024 | 20**/20** | 20**/20** | 20**/20** | 20**/20**
| Works Cost |  |  | 6340950 |  |  |  |  | 6340950
| Fees | 304365.6 | 405820.8 | 304365.6 |  |  |  |  | 1014552
| Non-works Costs |  | 120000 | [5 empty] | 120000
| Equipment Costs |  |  | 16513000 |  |  |  |  | 16513000
| Quantified Risk/ Contingency |  |  | 2398850.2 |  |  |  |  | 2398850.2
| Sub-total | 304365.6 | 525820.8 | 25557165.8 | 0 | 0 | 0 | 0 | 26387352.2
| Gross Vat | 60873.12 | 105164.16 | 5111433.16 | 0 | 0 | 0 | 0 | 5277470.44
| Less: Reclaimable VAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub-total | 60873.12 | 105164.16 | 5111433.16 | 0 | 0 | 0 | 0 | 5277470.44
| Total | 365238.72 | 630984.96 | 30668598.96 | 0 | 0 | 0 | 0 | 31664822.64
Funding source:
| Year | 0 | 1 | 2 | 3 | 4 | 5 | 6 | Total
| Financial year | 20**/20** | 20**/20** | 20**/20** | 20**/20** | 20**/20** | 20**/20** | 20**/20**
| Works Cost | [7 empty] | 0
| Fees | [7 empty] | 0
| Non-works Costs | [7 empty] | 0
| Equipment Costs | [7 empty] | 0
| Quantified Risk/ Contingency | [7 empty] | 0
| Sub-total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gross Vat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Less: Reclaimable VAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub-total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Funding source:
| Year | 0 | 1 | 2 | 3 | 4 | 5 | 6 | Total
| Financial year | 20**/20** | 20**/20** | 20**/20** | 20**/20** | 20**/20** | 20**/20** | 20**/20**
| Works Cost | [7 empty] | 0
| Fees | [7 empty] | 0
| Non-works Costs | [7 empty] | 0
| Equipment Costs | [7 empty] | 0
| Quantified Risk/ Contingency | [7 empty] | 0
| Sub-total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gross Vat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Less: Reclaimable VAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub-total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## PBC7
_________________________________________________________________________
Project Title |  | All Wales PET CT Programme
Option No |  | 4
Option Title |  | Cardiff plus 4 PET sites
_________________________________________________________________________
RECOVERABLE VAT CALCULATION
|  | a | b | c | d
|  | Cost Net of VAT | VAT at 20% (ie prior to recovery) | Percentage recoverable (% of col b) | Recoverable VAT (col b x col c)
|  | £ | £ | % | £
| Works Cost | 6340950 | 1268190 | 0% | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Fees | 1014552 | 202910.4 | 0% | 0
|  |  | 0 |  | 0
| Non-works Costs | 120000 | 24000 | 0% | 0
| Equipment Costs | 16513000 | 3302600 | 0% | 0
| Contingencies | -202910.4 | -40582.08 |  | 0
| Total |  |  | £ | 0

## New build
INSIGHT & ANALYTICS
BENCHMARKING REPORT –
Prepared for: | Mark Woodward
Office: | Liverpool
Date: | 2020-02-11
Prepared by: | Liz MacGregor
Notes:
All in TPI used: 331 1Q2020 (BCIS indices published 31 January 2020)
Location factor: | 88 North Wales (BCIS factors published 31 January2020)
Data used in the benchmarking exercise are as follows:Location Factor: 1.01
Key | Project Number | Base Date | Asset Description
A | BLQS1120 | 2012-06-06 | New build two storey community hospital the facility will include: 30 inpatient beds, a midwifery led maternity unit and a minor injury unit as well as diagnostic and X ray departments. The hospital will also offer on-going therapy and integrated rehabilitation services, an outpatient’s clinic and a day treatment centre.
B | BLQS1119 | 2009-09-07 | New build community hospital providing Inpatient, Diagnostics, Therapies, Outpatients and Community Health departments
C | CSRE0271 | 2008-11-24 | New build two storey community hospital
D | CSRE0209 | 2009-02-23 | New build hospital
E | CSRE0210 | 2006-10-30 | New build community hospital
F | CSRE0275 | 2010-03-04 | New build general hospital
G | CSRE0274 | 2010-03-04 | New build community hospital
H | CSRE0273 | 2003-11-01 | New build community hospital
0.98106
Key | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 |  | 9 |  | 10 | 12 | 13 | 14 | Total Cost | Update to 1Q 21
| Facilitating Works | Substructure | Superstructure | Finishings | FF&E | Services | Bldgs/Bldg Units | Extg Bldgs | sub total | External Works | sub total | Preliminaries | sub total | OH&P | Other Costs | Risk | Inflation
A | 2.58 | 304.8 | 1130.58 | 145.94 | 141.03 | 1168.04 | 0 | 0 | 2892.97 | 579.89 | 3472.86 | 970.44 | 4443.3 | 271.22 | 0 | 0 | 0 | 4714.51 | 4625.22
B | 38.66 | 476.26 | 985.13 | 130.12 | 115.69 | 1241.19 | 0 | 0 | 2987.05 | 237.7 | 3224.75 | 587.45 | 3812.2 | 292.62 | -91.49 | 170.04 | 0 | 4183.36 | 4104.1297
C | 0 | 153.62 | 1025.25 | 139.07 | 103.19 | 1149.61 | 0 | 0 | 2570.74 | 492.03 | 3062.77 | 526.4 | 3589.17 | 0 | 0 | 0 | 0 | 3589.17 | 3521.1933
D | 0 | 200.04 | 777.65 | 182.9 | 147.84 | 1106.14 | 0 | 0 | 2414.57 | 558.77 | 2973.34 | 401.1 | 3374.44 | 0 | 0 | 89.83 | 0 | 3464.26 | 3398.649
E | 0 | 94.64 | 748.88 | 117.47 | 91.78 | 898.32 | 0 | 0 | 1951.09 | 437.34 | 2388.43 | 453.69 | 2842.12 | 0 | 0 | 314.27 | 0 | 3156.4 | 3096.6197
F | 0 | 62.28 | 742.35 | 179.5 | 117.06 | 1027.78 | 0 | 61.59 | 2190.56 | 584.09 | 2774.65 | 199.4 | 2974.05 | 0 | 0 | 0 | 0 | 2974.06 | 2917.7331
G | 0 | 139.84 | 800.98 | 187.54 | 69.14 | 926.17 | 0 | 0 | 2123.67 | 523.14 | 2646.81 | 182.24 | 2829.05 | 0 | 0 | 0 | 0 | 2829.04 | 2775.4597
H | 0 | 111.38 | 680.14 | 199.69 | 151.58 | 926.21 | 0 | 33.67 | 2102.67 | 658.93 | 2761.6 | 0 | 2761.6 | 0 | 0 | 0 | 0 | 2761.6 | 2709.297
[17 empty] | MINIMUM | 2761.6 | 2709.297
[17 empty] | MAXIMUM | 4714.51 | 4625.22
[18 empty] | Say | 4000
plus 20% on Costs

## refurb
BCIS Online
Grade II listed office refurbishment
BCIS Online - #33315
Building function: | 320. - Offices
Type of work: | Rehabilitation/Conversion
Gross floor area: | 973 | m2
Job title: | Conversion, Reconfiguration and Refurbishment of Magistrates Court to Offices
Location: | Port Talbot, West Glamorgan
District: | Port Talbot
Grid reference: | SS7689
Postcode: | SA13 1SB
Dates: | Receipt: | 2018-05-11
| Base: | 2018-05-11
| Acceptance: | 2018-06-13
| Possession: | 2018-08-13
Project details: | Conversion of former Grade II listed magistrates court into 4Nr office units with external works. Stripping out services, partitions, windows, doors, finishes and fittings.
Site conditions: | Restricted site access and working space.
Market conditions: | Good.
Project tender price index: | 367 on 1985 BCIS Index Base
Client: | Neath Port Talbot County Borough Council
Tender documentation: | Bill of Quantities
Selection of contractor: | Selected competition
No of tenders: | Issued: | 6 | Received: | 6
Contract: | NEC3 priced contract 2013 (option A or B)
Contract period (mths): | Stipulated: | 33 | Offered: | 33 | Agreed: | 33
Cost fluctuations: | Fixed
Basis of cost: | Tender
Tender list: | 1747435 | -
| 1823921 | 4.4%
| 1842737 | 5.5%
| 1860560 | 6.5%
| 1879239 | 7.5%
| 1923721 | 10.1%
Contract breakdown
Measured work: | 1394496
Provisional sums: | 112000
Preliminaries: | 140939
Contingencies: | 100000
Contract sum: | 1747435
Accommodation and design features: | Conversion, reconfiguration and refurbishment of a former Grade II listed magistrates court into providing high specification office space with meeting and training rooms. Enclosed external glazed fire escape with strip foundations. Stonework and brick repairs. Built up felt and zinc pitched roofing. Staircase balustrading. Replacement aluminium windows. Metal stud partitions and glazed screens. Doors. Plaster, plasterboard, ceramic, emulsion and plastic wall finishes. Raised access floors, ceramic, vinyl and carpet floor finishes. Plasterboard and suspended mineral fibre ceilings. Kitchen units and blinds. Sanitaryware. Mechanical and electrical services. Lift alterations. Stripping out.
Accreditation scores: | Listed Building Grade II
Elements
Element | Total cost | Cost per m² | Element unit quantity | Element unit rate | Percentage
01 Substructure | (Costs included elsewhere) | 0 | 0
02 Superstructure | (Costs include other elements) | 519219 | 534 |  |  | 30 | %
03 Finishes |  | 170491 | 175 |  |  | 10 | %
04 Fittings, Furnishings and Equipment |  | 26076 | 27 |  |  | 1 | %
05 Services |  | 576336 | 592 |  |  | 33 | %
06 Prefabricated Buildings and Building Units |  | 0 | 0
07 Work to Existing Building |  | 0 | 0
Building Sub-total |  | 1292122 | 1328 |  |  | 74 | %
08 External Works |  | 177114 | 182 |  |  | 10 | %
00 Facilitating Works |  | 37260 | 38 |  |  | 2 | %
09 Preliminaries |  | 140939 | 145 |  |  | 8 | %
10 Main Contractor's Overheads and Profit |  | 0 | 0
Total (less Design Fees) |  | 1647435 | 1693 |  |  | 94 | %
11 Project/Design Team Fees |  | 0 | 0
12 Other Development/Project Costs |  | 0 | 0
13 Risk (Clients Contingencies) |  | 100000 | 103 |  |  | 6 | %
Total Contract sum |  | 1747435 | 1796 |  |  | 100 | %
|  |  | 2000 | Small works
Credits:
Submitted by |  | Neath Port Talbot County Borough Council
Client |  | Neath Port Talbot County Borough Council
Quantity Surveyor |  | Neath Port Talbot County Borough Council
General Contractor |  | TAD Builders Ltd
BCIS Online - #32689
Building function: | 320. - Offices
Type of work: | Rehabilitation/Conversion
Gross floor area: | 9290 | m2
Job title: | Office Refurbishment, Arkwright House
Location: | Manchester, Greater Manchester
District: | Manchester
Grid reference: | SJ8398
Postcode: | M3 2LF
Dates: | Receipt: | 2015-09-25
| Base: | 2015-09-25
Project details: | Refurbishment of 6 storey office block with external works. Asbestos removal.
Site conditions: | Works within existing building.
Client: | Catalyst Capital
Tender documentation: | Employers Requirements (for Design and Build)
Selection of contractor: | Design and build
Cost fluctuations: | Fixed
Contract breakdown
Measured work: | 16297332
Preliminaries: | 2877073
Contingencies: | 779337
Contractor design fees: | 254814
Contract sum: | 20208556
Accommodation and design features: | Refurbishment of 6 storey 1930's Grade II listed classicist offices with minor extension including ground floor lobby restoration to original form. Additional piled foundations. Steel frame. Curtain walling. Roof and wall cladding. New concrete floors. Partitions and ceilings. Raised access flooring. Ceramic tiling. Soft floor finishes. Painting. Fixtures and fittings. Mechanical and electrical services. Lifts refurbishment. Asbestos removal.
Accreditation scores: | Listed Building Grade II
Elements
Element | Total cost | Cost per m² | Element unit quantity | Element unit rate | Percentage
1 Substructure |  | 257541 | 27 |  |  | 1 | %
2 Superstructure |  | 6948000 | 748 |  |  | 34 | %
3 Finishes |  | 1214403 | 130 |  |  | 6 | %
4 Fittings and Furnishings |  | 139214 | 15 |  |  | 1 | %
5 Services |  | 6803030 | 732 |  |  | 34 | %
Building Sub-total |  | 15362187 | 1654 |  |  | 76 | %
6 External Works |  | 935144 | 101 |  |  | 5 | %
7 Preliminaries |  | 2877073 | 310 |  |  | 14 | %
8 Contingencies |  | 779337 | 84 |  |  | 4 | %
Total (less Design Fees) |  | 19953742 | 2147 |  |  | 99 | %
9 Design Fees |  | 254814 | 27 |  |  | 1 | %
Total Contract sum |  | 20208556 | 2176 |  |  | 100 | %
Credits:
Submitted by |  | Gardiner &amp; Theobald
Client |  | Catalyst Capital
Architect |  | Sheppard Robson
Quantity Surveyor |  | Gardiner &amp; Theobald
Structural Engineer |  | Curtins Consulting Ltd
Services Engineer |  | Crookes Walker Consulting
Planning Supervisor |  | Deloitte Real Estate