«Group»

Pacific Horizons (sample audit)

All Wales Positron Emission Tomography (PET) Service

Draft Internal Audit Brief

April 2021

Welsh Health Specialised Services Committee

NHS Wales Shared Services Partnership

Audit and Assurance Services

Contents	Page

1.	Introduction and Background	2

2.	Scope and Objectives	2

3.	Associated Risks	3

4.	Audit Approach	3

5.	Key Contacts	4

6.	Timing of the Review	4

7.	Audit Brief Agreement	4

Appendix A - Assurance opinion and action plan risk rating

Please Note:

This audit brief has been prepared for internal use only. Audit & Assurance Services reports are prepared, in accordance with the Internal Audit Charter and Annual Plan, approved by the Audit & Risk Committee.

Audit briefs are prepared by the staff of the NHS Wales Shared Services Partnership – Audit & Assurance Services, and addressed to Independent Members or officers including those designated as Accountable Officer. They are prepared for the sole use of the Welsh Health Specialised Services Committee and no responsibility is taken by the Audit & Assurance Services Internal Auditors to any director or officer in their individual capacity, or to any third party.

Introduction and Background

Our review of the Welsh Health Specialised Services Committee’s  All Wales Positron Emission Tomography (PET) Service Programme Business Case will be completed in line with the 2021/22 Internal Audit Plan.

### The Programme Business Case (PBC) is due to be completed shortly, and will set out the case for an All Wales Positron Emission Tomography (PET) Service with sufficient capacity to meet the projected demand for PET scanning over the next ten years with anticipated costs in the region of £28.5m.

The outcome of the review will inform the risk assessment for the future audit requirement at programme and/or individual projects.

Noting the ongoing impact of Covid 19, the delivery of this assignment will include an increased element of remote working. To accommodate the same, single points of contact between the audit and client teams will be established and information request schedules utilised.

Scope and Objectives

The overall objective of this audit is to evaluate the delivery of the programme and determine the adequacy of the systems and controls in place. The review will seek to provide assurance to the WHSSC Audit and Risk Committee that risks material to the system’s objectives are managed appropriately. The areas that the review will seek to provide assurance on are:

- Governance –

  - Programme governance arrangements are sufficiently defined, implemented and aligned with existing corporate governance structures.

  - The programme governance arrangements sufficiently identify and engage key parties/ external key stakeholders.

  - Executive ownership and leadership is demonstrated at the programme.

  - Key groups/meetings have been established and implemented to support the delivery of the programme.

  - Remaining key roles have been allocated and the associated resource requirement has been determined, costed and implemented.

- Decisions and Approvals –

  - Appropriate key decisions and approvals have been obtained at key junctures.

  - The Programme progresses within these approvals.

  - Decisions and approvals are recorded appropriately and demonstrate support from key stakeholders.

- Monitoring & Reporting –

  - Expected monitoring and reporting arrangements have been sufficiently defined.

  - Arrangements are in place to ensure the accuracy, frequency and circulation of key programme performance information.

  - Information is routinely and sufficiently challenged, to assist management decision making.

- Risk Management –

  - There is a defined approach to risk management at the programme.

  - Risks have been identified, recorded and appraised using recognised management techniques.

  - Risks have been assigned to those best placed to manage the risk, with appropriate/ timely management action.

  - Where possible, risks have been quantified to inform the proposed management action.

- Other issues -

  - Any other issues that may impact the assurance provided, including performance against project objectives (e.g. time, cost, quality, benefits, critical success factors etc.).

Associated Risks

The potential risks considered in the review are as follows:

- Governance arrangements are weak leading to a loss of control on project objectives.

- The programme progresses outside of agreed approvals and at significant financial and/or reputational risk.

- Monitoring and reporting is insufficient, impacting the ability of management to make informed decisions.

- Risks are poorly managed impacting on programme costs and programme.

Audit Approach

The approach to audit assignments is risk based, where the risks are identified with the lead manager. Controls are identified to manage those risks and the assignment scope designed to provide assurances on those controls.

The work to be undertaken as part of this review will include:

- Obtaining, reading and understanding relevant policies, procedures and documentation.

- Meeting with key staff to discuss processes.

- Undertaking sample testing where applicable.

The outcomes of this review can be linked or contribute to the Assurance Framework and also the NHS Wales Health and Care Standards.

The audit assignment will be allocated an assurance rating, dependant on the level of assurance Internal Audit are able to provide. There are four potential levels of assurance available, along with three recommendation priorities described in Appendix A.

### As indicated previously, noting the impact of Covid 19, the delivery of this assignment will include an increased element of remote working.

### Any limitations to the audit fieldwork as a consequence of the Covid 19 restrictions will be clearly outlined at the subsequent report.

Planning field

Key Contacts

| Name | Designation |
| --- | --- |
| Stuart Davies | Director of Finance |
| Sarah McAllister | Programme Manager |

Additionally, we reserve the right to liaise with Audit Wales, Welsh Government, NWSSP (SES) or any other parties pertinent to the review.

Timing of the Review

Target dates for the progression of the audit fieldwork are to be agreed with the client at the initial audit set-up meeting.

| Audit area | Target dates |
| --- | --- |
| Fieldwork | TBD |
| Debrief meeting | TBD |
| Management Response | Within two weeks of the draft report issued |

Audit Brief Agreement

The Director of Finance is requested to formally agree this audit brief by e-mail.

Appendix A - Assurance opinion and action plan risk rating

Audit Assurance Ratings

Substantial assurance - The Board can take substantial assurance that arrangements to secure governance, risk management and internal control, within those areas under review, are suitably designed and applied effectively. Few matters require attention and are compliance or advisory in nature with low impact on residual risk exposure.

Reasonable assurance - The Board can take reasonable assurance that arrangements to secure governance, risk management and internal control, within those areas under review, are suitably designed and applied effectively. Some matters require management attention in control design or compliance with low to moderate impact on residual risk exposure until resolved.

Limited assurance - The Board can take limited assurance that arrangements to secure governance, risk management and internal control, within those areas under review, are suitably designed and applied effectively. More significant matters require management attention with moderate impact on residual risk exposure until resolved.

No assurance - The Board has no assurance that arrangements to secure governance, risk management and internal control, within those areas under review, are suitably designed and applied effectively.  Action is required to address the whole control framework in this area with high impact on residual risk exposure until resolved.

Prioritisation of Recommendations

| Priority Level | Explanation | Management action |
| --- | --- | --- |
| High | Poor key control design OR widespread non-compliance with key controls. PLUS Significant risk to achievement of a system objective OR evidence present of material loss, error or misstatement. | Immediate* |
| Medium | Minor weakness in control design OR limited non-compliance with established controls. PLUS Some risk to achievement of a system objective. | Within One Month* |
| Low | Potential to enhance system design to improve efficiency or effectiveness of controls. These are generally issues of good practice for management consideration. | Within Three Months* |

In order to assist management in using our reports, we categorise our recommendations according to their level of priority as follows.

* Unless a more appropriate timescale is identified/agreed at the assignment.