Programme Business Case 
for an All Wales Positron Emission Tomography (PET) Service

Blueprint

Purpose and Summary of Document:

The purpose of the Blueprint is to provide a model of the capability that must be in place to support achievement of the Vision of a Programme.  It provides the focus for delivering the changes to the service that will meet continuing and evolving needs of the population of Wales.

Intended Audience:

This document is intended to be read by the All Wales PET Strategic Programme Board and key stakeholders. It is assumed that the intended audience will be familiar with:

- PET Services in Wales, its challenges and opportunities

- The intended scope/drivers of the Programme

- The role of AWPET (All Wales PET Advisory Group)

- 2018 Statement of Intent

Publication/ Distribution:

All Wales PET Strategic Programme Board

Version history

| Version | Date Issued | Brief Summary of Change |
| --- | --- | --- |
| 0.1 |  |  |

Authors: Sarah McAllister

Senior responsible Officer: Sian Lewis

- Introduction

Positron Emission Tomography (PET) has become a central diagnostic tool in the management of cancer and other non-cancer conditions. Its role and the evidence base continues to evolve. Although it is a relatively expensive investigation, when used appropriately PET can increase the value of healthcare overall, supporting the principles of prudent healthcare.

PET can significantly improve clinical decision making, particularly with respect to the appropriate use of complex and expensive specialist treatments. There is an increasing body of high quality evidence demonstrating the value of PET to improved patient outcomes in a number of areas. There is also excitement in both the clinical and research communities about the use of PET in a rapidly growing number of new indications and new radiopharmaceuticals.

The latest scanners combine both the functional information of PET and the structural information of Computed Tomography (CT) into one machine, resulting in a fused and detailed PET-CT scan.

In the UK, the development of PET services has been slow compared with other European countries. The development of PET in Wales lags significantly behind the other three devolved nations, in terms of funded indications for PET scans, development of PET scanning infrastructure, specialist workforce, and research opportunities. It is estimated that Wales is currently performing approximately 40% of the PET scans per head of population compared to England. NHS Wales has a list of funded indications for PET-CT which is limited compared to England and Scotland.

Demand for PET scanning is increasing, with demand growth between 12 and 16% per annum. Wales needs to close the gap and provide a PET service that is in line with comparator countries so that Welsh citizens may benefit from the provision.

On 28th March 2019, the Director General, Health and Social Service/NHS Wales Chief Executive, Welsh Government, wrote to the Chair of the AWPET Advisory Group, endorsing the recommendations made in the report and outlining the expectations for NHS Wales to collaborate on their implementation.

Since there was recognition that additional capital investment was required, to enable the broader service to be developed and made equitable for people across Wales. The Director General requested that WHSCC develop a Programme Business Case with support from the National Imaging Network, to guide the development of future service provision for the whole of Wales.

- Vision Statement

Programme Vision

By 2031 we will deliver a PET service of excellence which provides patients with equitable access to the latest technology, research and brilliant staff that compares with the best across Europe. It will help us to improve survival rates and quality of life for people with cancer in Wales

Programme Aim

The aim of the Programme is to build on the work of the All Wales PET Advisory Group by developing greater strategic focus on the development of sustainable services over a ten year period. This will include bringing the financial, workforce, infrastructure and planning solutions to bear on the issues facing the service.

The nationally directed Programme will oversee a programme of work that will deliver sustainable and high quality PET services across Wales. Features of the service in a business as usual end-state, will show responsive demand and capacity planning and will be delivering clear quality outcomes through modern facilities, optimally configured workforce in fully accredited units and with assured supply of radiopharmaceuticals. Ultimately, this Programme will ensure that the population of Wales will have equitable access to high quality PET scanning and research, in line with best practice across the UK and Europe.

The aims of this Programme are to:

- plan an infrastructure of high quality PET-CT scanning facilities across Wales which meets the growing demand and is compliant with the WHSSC PET service specification;

- ensure that the agreed infrastructure takes into account the sometimes competing priorities of patient access, cost, workforce capacity, training and research;

- ensure that the agreed infrastructure provides resilience and a culture of excellence through co-operative working between providers;

- support PETIC in developing a business continuity plan during recommissioning of its facilities within the next 12 months;

- support the development of research and development to facilitate world class R&D clinical improvements;

- develop the strategic vision for PET-CT services in Wales up to service implementation, and

- develop an end to end clinical process for radiological reporting of scans in Wales.

Measuring success

We will know if we have succeeded when core capacity is available to meet the clinical demand of PET scanning which includes scanners and workforce; when services routinely meet diagnostic turnaround times with little variation; when breaches in PET scanning waiting times are rare; when Welsh patients are able to easily access and participate in clinical trials and when relevant health board sites have achieved WHSSC PET Service Specification.

- Programme Phasing

The programme approach is described as being in four phases. In order to set context, a current state of service is provided below:

3.1	Current state of business operations

- Significant capacity constraints with just one fixed analogue PET scanner in place across Wales and externally sourced mobile scanning provision for South West and North Wales just two days a week.

- Clear growing demand through widening of indications commissioned for scanning.

- The fixed scanner in South East Wales is past its useful age.

- There are significant issues and constraints with access, quality and patient experience with mobile scanners.

- There is significant issues with workforce numbers and skill-set, with an external service supplier providing a workforce to run mobile scanners.

- Not enough patients are able to access PET scans or clinical trials, and existing services are inequitable to patients due to the issues of mobile vs. fixed scanners.

- There are issues with IT surrounding referrals and sharing of reports.

- There are issues facing radiopharmaceutical provision, with South East Wales benefiting from a cyclotron that can manufacture radiopharmaceuticals but not able to supply south Wales due to licensing rules. In addition there are issue for North Wales supply and seeking assurances for the future provision.

- No national overview of physical estate and supporting infrastructure (condition and capacity).

  - Programme Phases

The delivery of this programme is a significant undertaking. PET scanning services in Wales have a generational opportunity to set themselves up on a long-term sustainable footing.  At the same time, the service must also deliver improvements on shorter-term capacity issues, faced through the somewhat critical condition of the PETIC scanning facilities in Cardiff.

The Programme and Health Boards will need to manage a mix of timelines and the risks and benefits associated with what is done to address short to medium term challenges and the impacts that those interventions have for our patients and the future services they will be using.

Phasing the programme will enable tight management of delivery, programme risks and enable managed assurance around delivery i.e. the board will be able to mandate delay or expedition of each phase. The Programme has been divided into tranches, within which are Projects that will undertake the installation of a modern digital PET scanner and associated facilities. Three supporting workstreams will run for the duration of the Programme and support the wider infrastructure during implementation: workforce, centres of excellence and radiopharmaceutical provision.

The first six years of the programme are described in six phases as outlined below:

|  | Description | Duration | Timeline |
| --- | --- | --- | --- |
| Phase 1 | Set-up and establishment of Programme groups and leads | 2 months | May 2021 – June 2021 |
| Phase 2 | Set-up, initiation and establishment of digital PET Scanner at PETIC and cyclotron upgrade | 10 Months | July 2021 – April 2022 |
| Phase 3 | Set-up, initiation and establishment of digital PET Scanner at Swansea, including site build | 26 months | July 2021 – September 2023 |
| Phase 4 | Set-up, initiation and establishment of digital PET Scanner in North Wales, including site build | 30 months | July 2021 – January 2024 |
| Phase 5 | Review and determine future arrangements – go/no-go on fourth scanner | 3 months | July 2023 |
| Phase 6 | Set-up, initiation and establishment of digital PET Scanner in South East Wales (location TBD), including site build | 42 months | December 2023 – June 2027 |

  - Final states to be achieved by end of each Phase:

By end Phase 1:

- Functional programme governance and structure in place, all work streams established with leads appointed and work plan developed.

By end Phase 2:

- Completed installation of a digital PET scanner and upgraded cyclotron at PETIC, which will avert critical service failure and increase scanning capacity so that benefits can begin to be realised for patients, workforce and the wider NHS in South East Wales.

By end Phase 3:

- Completed installation of a digital PET scanner and upgraded facilities at Swansea, which will increase scanning capacity so that benefits can begin to be realised for patients, workforce and the wider NHS in South West Wales. This will also generate outputs that will contribute toward a step change in reaching the Spending Objectives of the Programme.

By end Phase 4:

- Completed installation of a digital PET scanner and new built facilities at a location in North wales, which will increase scanning capacity so that benefits can begin to be realised for patients, workforce and the wider NHS in South West Wales. This will also generate outputs that will contribute toward a step change in reaching the Spending Objectives of the Programme and contribute to the Spending Objectives of the wider Nuclear Medicine Consolidation Programme.

By end Phase 5:

- A thorough understanding of real-time clinical demand data, which can be compared against the clinical demand model. An opportunity to assess workforce and wider infrastructure needs for a potential fourth PET scanner and an assessment of potential location(s). This phase will serve as a go/no-go decision point for Phase 6.

By end Phase 6:

- Completed installation of a digital PET scanner and new built facilities at a location in south Wales, which will answer the final scanning demand needs. This final phase will mean that the Programme benefits will be realised for patients, workforce and the wider NHS in South West Wales. This will also generate outputs that will contribute toward a step change in reaching the Spending Objectives

- Scope of Change

Programme blueprints use the POTI model as a way to define the scope of what is going to change once all the projects in the programme are complete. POTI sets out the scope of the programme at a high level: Processes, Organisation, Technology and Information.

2.1	Processes

This is what PET services across Wales must be doing to support its purpose and meet the needs of its patients. There will probably be a combination of new and amended business processes and service performance requirements will include:

- Referral pathway development with Cancer, Neurology and Rheumatology networks

- Increased throughput (volume)

- Consistent process indicators (waiting times)

- Sustainable planned capacity

- Designs for the service expansion of PET scanning for radiotherapy treatment planning

- Plans for the delivery of the expansion of clinical research activity and innovative developments in PET service provision

- Resilience – hold an ability to respond to increased workload or reduced specialty or other staffing availability

- Improving clinical outcomes through appropriate commissioning through an evidence-based mechanism

- Providing equitable access to PET scanning across Wales

- An assured supply of MA licensed radiopharmaceuticals and those under Specials and IMP licenses

2.2	Organisation

The optimal configuration and governance arrangements for PET services in Wales will include new/amended elements of business management with developed national principles for:

- Service structure: the service will involve fixed scanners based within some Health Boards, to which surrounding Health Boards will refer in to. These sites will create Centres of Excellence.

- Functions & roles: there will be a resilient workforce with appropriate skill-mix to deliver a high-quality and efficient service.  Roles will include: Clinical Radiologists, Radiographers, Clinical Scientists/Medical Physics Experts, Clinical Support Staff, Administrative Staff, Finance Business Partner and PET/CT Manager.

- Locations: the future PET scanners will be placed in Cardiff, Swansea, with a scanner also in North Wales. Further scanner(s) will be located to answer clinical demand, population density and consideration of the feasibility of surrounding infrastructure.

- Teams: the programme will be hosted by WHSSC, with a programme manager responsible for delivery. Each PET scanning site will have a Lead and they will feed into the AWPET Group and report KPIs to WHSSC on a quarterly basis, with consistency across sites. The AWPET group will continue to advise the WHSSC on an evidence–based approach to commissioning PET scanning. Each scanner will an asset of the hosting organisation and be answerable to local governance arrangements for this.

- Training: existing staff will be offered training so they can benefit from personal development and provide a resilient workforce. There will be an attraction of new staff to the Centres of Excellence.

- Research: there will be an open and collaborative approach to research, with cross-site partnerships for clinical trials. There will be partnerships with academic and private sector organisations.

- Stakeholders will be wide and varied.  These include: Collaborative, Health Boards, HEIW, NIAW, IWEG, academic institutions, Cancer network [EXPAND]

- National programme/network arrangements: the All Wales PET Service will be part of the wider National Imaging Strategy Programme Board to ensure that cross-modality impacts are considered.

2.3	Information

The data and information that the organisation will require in order to deliver to its customers:

- Nationally agreed data sets which include consistent coding of scans across all sites.

- Nationally agreed standards and measures – this will fall within the upgraded PACS and RADIS system which the RISPP is delivering. [EXPAND].

- Nationally agreed performance reporting (KPIs) which will be reported consistently to WHSSC.

- Information on staffing and competency levels will need to be kept up-to-date at PET sites to maintain sufficient skill-mix.

2.4	Technology, Tools, Equipment, Facilities

There is a significant need to update and upgrade much of the technology that exists for the All Wales PET service. These include:

- Digital PET scanners that are AI-ready.

- Supporting equipment that will facilitate future development of services, such as radiotherapy planning lasers, flat beds, robotic radiotracer dispensers.

- Modern, warm and welcoming facilities with sufficient numbers of uptake rooms to facilitate throughput and sufficient numbers of “hot” toilets

- A flexible working style, collaborative behaviours and culture.