| Objective | Specific Actions | How will we know the objective has been achieved? | Who will lead this objective? | predicted completion date |
| --- | --- | --- | --- | --- |
| - Develop branding for the UHB’s job advertising and career promotions | - Work with Media resources to develop a specific brand for promoting UHB’s job opportunities - Develop marketing and specific job promotions | - UHB jobs adverts and promotions have a recognised image - Brand will be used across multiple media platforms | Asst Director of Workforce Resourcing | 31 March 2023 |
| - Develop a career promotion plan | - Develop and implement an annual recruitment event calendar - Work with media resources and professions to develop career videos - Develop careers information for the various professions within UHB (Digital and Print) - Promote NHS careers at local schools, colleges and universities. | - Annual recruitment event calendar developed. - Job Promotions held at Schools and colleges - Career video library/website in place | Asst Director of Workforce Resourcing | 31 January 2023 |
| - Develop and expand a whole systems approach for temporary staffing across multiple professions and roles | - Review nurse bank and implement improvements as appropriate. - Undertake full process mapping to develop SOP - Implement and promote facilities bank - Maximise opportunities to include other professions/roles within a temp staffing bank - Merge staff banks following full implementation of Allocate Health Roster | - Any risks identified and action in place to reduce risk - SOP in place that will provide a clear process map for function. - Facilities bank has a high number of temporary staff available - A good supply of professions other than nursing are available on bank - All temp staffing work as one service to achieve consistency of process and economies of scale | Asst Director of Workforce Resourcing | 31 March 2023 |
| - Identify and attract new recruitment groups e.g. ex-military, minority ethnic groups, people with disabilities etc. | - Maximise apprenticeship opportunities within UHB (to include clinical apprentices) - Develop links with those under represented groups to promote job opportunities. - Create work experience opportunities - Work with LAs to support job opportunities for refugees | - New role adopted and implemented in clinical areas - Careers events held with groups in local community to promote C&V UHB as employer of choice - Work experience placements provided. - Refugees offered jobs within UHB | Inclusion Resourcing Manager | 31 October 2022 |
| - Review and adapt the recruitment process within the NWSSP parameters to simplify the recruitment process | - Identify opportunities to fast track part of the recruitment process for specific schemes - Review recruitment process from an applicant’s perspective with a view to simplifying - Work closely with NWSSP to influence change | - Improvements to process implemented - Survey of applicants undertaken and views collated. | Head of HR Operations | 31 March 2023 |
| - To develop and implement an action plan to improve staff retention. | - Undertake an in-depth analysis of LTO across the various professions and directorates. - Review and improve exit questionnaire/interview response. - Provide directorates with data and advice to reduce turnover - Starter questionnaires implemented | - Review undertaken, key themes identified as reasons for leaving - All staff who resign receive an exit questionnaire. Format is more user friendly. Increase in data received - Directorates are provided with data that will enable them to make improvements where required. - All staff receive a starter questionnaire after 3 months of commencing in the UHB | Graduate Trainee | 31 August 2022 |