## Risk Log
Risk Log
| Project Name: |  | South East Wales Vascular Network |  |  | Reporting Date: |  |  |  | 2021-09-01
|  |  | Victoria Le Grys | [5 empty] | Date updated: | 2021-08-26
Please hover over the title boxes for guidance on each column
[5 empty] | Current Risk | [5 empty] | Mirtigated Risk
ID | Date Raised | Workstream | Risk Event / Cause | Risk Effect /Impact | Impact | Likelyhood | Score (I xL) | Status | Response Category | Response / Mitigation Action | Impact | Likelyhood | Score (I xL) | Additional Controls | Control Adequecy ? | Action updates | Date of next review | Programme Owner | Actioner
R007 | 1/14/2020 | CAG | Unable to access surgical patient information between CAV & AB | Unable to deliver an effective service & delay in implementation of the programme | 4 | 4 | 16 | Open | Avoid | Meetings to date have not identified critical risks to go live but agreement that pursuit of optomised digital support should be persued with urgency. Letter sent from CEO's to DHCIW. CIO ABUHB to continue workstream to develop year 1 plan, costs identified within PBC | 4 | 2 | 8 |  | Adequate |  | 2021-09-13 | Mike Ogonovsky | MO
R013 | 1/14/2020 | CAG | No hybrid theatre provision in the proposed Hub | Unable to achieve maximise surgical patient outcomes | 4 | 4 | 16 | Open | Reduce | Project in place for the provision of a Hybrid theatre in the Hub. Interim Kit options appraisal to be drafted and reviewed with clinical leads from all Health Boards and signed off at Steer Co before inclusion within the business case | 3 | 3 | 9 |  | Adequate | OBC submitted to WG, scruitiny responses submitted, Scheduled for WG Infrastructure Board in September. Work continues on completing design brief as part of FBC submission Dec 21 | 2021-09-13 | CAV - capital management group. Interim measures CAG | VLG
R014 | 1/14/2020 | Finance | No comissioning model agreed | Delay on programme delivery | 4 | 2 | 8 | Open | Reduce | Set up finance sub-group, identify leads for each area. Obtain data required for analysis. | 4 | 1 | 4 |  | Adequate | Comissioning model agreed at Finance group and submitted within PBC | 2021-09-01 | Programme Board | Rob Holcombe
R019 | 2020-04-01 | Workforce | Hard to fill and long recruitment timescales for key posts to enable required capacity within Hub | Unable to launch Network within timescale | 4 | 4 | 16 | Open | Reduce | Review of overall hub capapcity planning to ensure safe go live with required theatre sessions and ward beds. CAV required to go out to advert, assesment that financial risk small due to existing vacancies within key areas. posts could be absorbed. CEO support for early recruitment required for number of key posts. | 4 | 4 | 16 |  | Inadequate | Recruitment commenced for Hub theatres, ward and Radiology at risk. Plan for 100% of these to be filled by Nov 21. Early req for recruitment to other key posts not confirmed, SBAR resubmission for 07.09.21. Readiness assessments WK beg 20/09 | 2021-09-13 | Programme Board | Mike Bond
R021 | 2020-05-11 | Commissiong | Cost increases not justifiable to the aims of the Programme | Delay or inability to launch Network | 4 | 4 | 16 | Open | Reduce | Hub and spoke planning templates and scruitiny process set out to include Peer Review of case | 4 | 3 | 12 | D&C review to be undertaken to assess variation in 19/20 refresh | Adequate | business case review at Programme Board. Finance group leading on comissioning model | 2021-09-07 | Programme Board | Rob Holcombe
R022 | 2020-05-11 | Commissiong | Inability to track activity accurately post go live | Inability to accurately/adequately fund service, inability to ensure Network pathways and model is being delivered as proposed. | 4 | 3 | 12 | Open | Avoid | Existing systems within CAV reviewed and data capture confirmed. MDT coordinator and network coordinator in PBC to ensure data completeness. Network and clinical lead to oversee timely delivery of data and quality. | 4 | 2 | 8 |  | Adequate |  | 2021-09-09 | Mike Ogonovsky and Mike Bond | Tina Bayliss
R023 | 2021-06-16 | CAG | Failure to deliver SEWV network will impact on key interdependent services (IR) | Failure to achieve the SEW vascular network will make it harder to recruit and so, in the medium term detrimental consequences for the variety of medical and surgical services that depend upon it. | 4 | 4 | 16 | Open | Avoid |  | N/A | N/A | N/A | For flagging at SEWN Exec programme Board. Agreed this is not a risk to delivery of the programme but is a wider risk around the delivery or IR services within the region which will be impacted further should the programme fail to deliver
R024 | 2021-06-16 | Operational | Lack of agreed surgical job plans leading to delays in implementation | A delay in receiving current job plans has led to a delay in agreement for proposed job plans for the network. | 4 | 4 | 16 | Open | Avoid | Proposal for workplans for Hub and CAV/CTM spokes have been distributed. Local reviews undertaken with AB. KC & DMc to lead with MB & GM | 4 | 3 | 12 |  | Inadequate | Meeting 20/08 to agree job plans for surgeons and junior doctor proposals, no agreement reached. suggest increase in probability score | 2021-09-13 | Operational & clinical leads CAV/AB/CTM UHB | KC/DMc
R024 | 2021-06-28 | Operational | Impact of COVID-19 increase in admissions may impact on capacity within the hub | Delay to implementation | 4 | 4 | 16 | Open | Avoid | Bi monthly review at Op Group. Readiness assessment to be undertaken to assess Hub capacity plans and provide assurance for go live | 4 | 4 | 16 |  | Inadequate |  | 2021-09-13 | Mike Bond

## Closed Risks
R003 | 1/14/2020 |  | Operational | Operation Group | Collapse of Interverional Radiology provision in Cwm Taf Morganwg | Unable to proceed with Vascular procedures in CTM | 4 | 5 | 20 | Closed | Avoid | Temporary urgent arrangements in place for CTM patients to come into CAV as Phase 1 of programme | 4 | 5 | 20 | full delivery of Programme required in order to further mitigate
R002 | 1/14/2020 |  | Operational | CAG | Difficult to recruit Vascular surgeons into comparitively small UHB's compared to other regional vascular services both locally and UK wide. | Medical workforce availability and sustainability limited with specialist Vascular surgeons available across the South East Wales region. | 4 | 4 | 16 | Open | Reduce | Successful delivery of the programme will attract candidates to SE Wales. Project governance in place through the regional vasular clinical advisory group, medical workforce is an identified deliverable. | 4 | 3 | 12 | Long term succession and recruitment planning required. |  | Note this is an operational risk currently and not a programme risk - advice to close | Recruitment plan in place | No recruitment plan developed after consultation phase
Robust plans required to ensure throughput of junior staff into a vascular career.
R012 | 1/14/2020 | Closed | Programme | Engagement & Consultation | Lack of robust engagement and consultation process | UHBs open to legal challenge. Patient and staff concerns may not be raised | 4 | 4 | 16 | Open | Avoid | critical path for engagement and consultation, mapped. engagement & consultation group set up and well attended with robust plan being delivered for engagement. Good ongoing engagement with CHC colleagues. | 3 | 3 | 9 |  | Adequate | Final report submitted to CHC's & Boards May 21 with support for implementation. Closure agreed at Steer Co 16/21 |  |  | 16/06/21 - date of closure | Chris Dawson Morris, chair | VLG
R009 | 1/14/2020 |  | Programme | Operational Group | Capacity and demand modelling outstanding | Unable to create a workforce model, Unable to identify theatre requirements. Unable to submit BCs and will impact on a successful engagement and consultation | 5 | 5 | 25 | Close | Avoid | Further detailed analysis of Critical Care demand and demand for transport. DH leading transportation alongside MJ & DK | 4 | 1 | 4 | Further data & clinical review of cases to be provided to WAST for review. 2016 data to be used as estimate and test | Adequate | Suggest close upon completion of Critical Care and transport demand level detail |  |  | 2021-06-16 | Tina Bayliss, Chair
R018 | 2/17/2021 |  | Programme | Engagement & Consultation | Pre-Election Period to be set for 25th March 2021 | Unable to hold public engagement events during the pre-election period. May delays engagement period end date and to programme timelines or affect robustness of engagement leading to requirment for further engagement | 4 | 4 | 16 | Close | Reduce | Spoken to Chair of Programme board and Consultation Institute and CHC for advice. Agreed to commence engagement with a mid point review. All public events moved to be completed prior to 25th March with responses remaining open. | 3 | 1 | 3 |  | Adequate | Link to R012. suggest close following Board support |  |  | 2021-06-16 | Chris Dawson Morris
R020 | 2020-05-10 |  | Programme | Workforce | Delay to staff consultation due to delay on Spoke MOC agreement to ensure posts in scope are identified. Consultation timetable was to issue document for comment by the end of May giving staff and staff side ample time to comment (4 weeks). | Unable to launch Network within timescale set | 4 | 4 | 16 | Closed | Avoid | Early engagement with staff side to negotiate implementation dates if staff are required to rotate across the network in particular via an honorary contract. | 4 | 1 | 4 | Workforce leads to develop plan, distribute information about possible hub posts | Not adequate | Workforce revirew across Health Boards has not suggested that there will be many staff groups transferring. Some interest within CTM for taking up CAV posts. Limited requirement for consultation. Requires completion of future job plans in order to identify any transfer of anaesthetic consultant session. |  |  | 2021-06-21 | Workforce Leads - link to above Spoke clinical and planning leads | TW/CB/AC
R005 | 1/14/2020 |  | Operational | Operation Group | Limited capacity in relation to beds and theatre in the hub. | Unable to deliver an effective service | 4 | 4 | 16 | Open | Avoid | Refresh Demand and Capacity modelling and benchmarking. Operational group set up to review flow and issues. | 3 | 2 | 6
R006 | 1/14/2020 |  | Programme | CAG | Lack of concensus of model of care for patients and patient pathways for the network | Unable to deliver an effective service. Delay implementation | 4 | 4 | 16 | Closed | Avoid | Overarching Network specification agreed. Spoke Models of Care to be completedand signed off at CAG/Op group and SC. Early engagement of relavent required areas/services. Rehab model to feed in accordinaly to Hub and Spoke groups to inform planning | 4 | 4 | 16 | Spoke MOC to be approved locally by Health Boards with MD sign off, Joint MD review of models of care, pathways and network specification | Adequate | MD review completed, CAV & CTM supportive, AB supportive of high level rasied concerns following meeting re level of detail required to support discussion at Programme Board |  |  | 2021-06-16 | UHB clinical leads & MD's | VLG