## Q1 progress update
Key | Unfunded, Business Case TBD |  |  | Trend
| Some funding but not enough to complete the work / some unknowns on funding |  |  | Off track
| Funded and barring other priorities we expect to complete the work |  |  | Going off track
| Outside of CAV control |  |  | On track
Complete
| IMTP MILESTONES | PLANNED Q1 SUBJECT TO RESOURCE | UPDATES ON Q1 PLANNED WORK | TREND | REASON
| Electronic Patient Record | Refresh solution architecture work and soft market testing update | Initial user research work complete; lack of resource delaying further progress; Enterprise Architecture to be developed - working with Channel3 on this. UI tools being investigated by team following UX work | On track | Lack of resource
| Digital front door | Virtual ward / home location in EAMD, medicine and surgery; existing WCWS functionality ported across to EUWS | New functionality has been added to EUWS e.g. Results, Nutrition, clinical notes, frailty score, Dr handover notes, medicine reconciliations. We are also developing the ability for transfer of care data to be available so that can view how long in ED, how long in an assessment unit, through other settings and then discharge. | On track
| Econsent | Decision on piloting E-consent | Discussion pending on whether we progress this in 22/23 or 23/24 | Off track | As update
| Patient facing content | Patient facing content published for targetted areas - c130 leaflets | 20 leafelts completed by year end, work started on 336 however clinical time unavailable, plan and templates etc with comms team - no further reporting by D&HI | Complete
| Digital comms & Choose and Book | Digital comms ITT specification finalised inc. hybrid mail, patient portal, digital post, choose & book for patients | Still planned, aim to complete ITT by quarter end | Off track | Lack of resource
| DSPP NHS Wales App (from DSPP) | No milestone this quarter
| PROMs | PROMs platform integrations and 1st service areas live | NETS live 23/05, Myeloma and MSK live in June. 40+ service areas waiitng. St Grp being established. Clinical lead identified, awaiting operational lead. Early task is to agree priroitisation. Meanwhile we complete the remaining pilot service areas that have already been agreed | Going off track | Illness
| Shared health and care records using LDR | Next Use Cases agreed for 22/23; Continued build out of LDR; Evaluation of LACS LDR pilot | no DPIF funding tp progress more use cases, evaluation LACS in progress | Off track | No funding
| Self directed enquiry management | No milestone this quarter
| Outpatients transformation | SoS & PIFU spread and scale; SOS and PIFU technical approached to be extended across MH and community; referrals internally and from primary and community care | Algorithm built for acute enabling automatic discharge on SoS ticket expiry. Not yet in place for community. PIFU automated patient contact functionality will be built when process design completed. | On track
| Community, Mental Health and PCIC services | - Complete the onboarding of outpatient Physiotherapy, Speech and Language, Dietetics, COVID Rehab, Long COVID, and associated CD&T services into clinical e-record keeping (via PARIS) | Digital Therapies launched to both co-ordinate and sequence work packages for Q1 & Q2. Refreshed prioritisation model will now allow re-progression. | Going off track | Reconsidered Governance following launch of 'Digital CD&T'.
| Digital dictation & Transcription | Lite versions implemented /available UHB wide | Over 200 clinicians currently using, c180 med secs using and a further 360 colleagues waiting to be trained; integration conversations have started | On track
| eTR radiology & GPeTR | GPeTR into production; eTR modalities in local acute solution review checkpoint | GPeTR live rolling out managed by radiology; Powerapp built for acute built, being tested (v1.0). Launch dependent on recruitment and a technical solution for the App to consume data from acute PAS | Going off track | Gateway delays & additional changes requested
| Clinical/specialty applications | ePMA procurement (off back of DHCW framework); Outpatients module stapled into WCP; SNOMED CT live in PMS & PARIS | ePMA national framework delayed; resources to start project to be funded by WG, programme managed by Pharmacy. Agreement given to staple WCP & COMII - development to be completed by CAV; SNOMED look-up available, internal project to be initiated subject to resources to incorporate and that activity is coded - acute & community | Off track | National procurement being re-run
| Interoperabilty | Integrations with PROMs, digital dictation etc ; Internal interoperability between major PAS (acute, community/MH and others) | Planning work has started, resource challenges inhibit progress | Off track | Lack of resource
| Scan4Safety | Project initiation and one theatre already baselined | Project has started in cardiology (theatres), baselining nearly complete; PM being recruited. Governance in place, jointly managed with NWSSP as part of national programme | On track
| Vein2Vein transfusion (all Wales) | Hardware in place - see update. All Wales business csase to be completed. | WG funding initial discovery work to create an all Wales business case. This programme is expected to tie in with the national LINC programme. Project managed by Blood Transfusion Service. Digital are supporting however it is not driving this programme. No further reports will be provided. | On track
| PowerBI | Evaluation of platforms | Lack of resource, push back until resourcing resolved | Off track | Lack of resource
| Use Your Own Device | The ability to access all applications remotely includng on your own device# | Internal discussions to be held about what the right solutions for hybrid working and remote access including your own device can be | Off track | Lack of resource
| Managed print/Follw Me printing | No milestone this quarter
Key | Unfunded, Business Case TBD
Some funding but not enough to complete the work / some unknowns on funding
Funded and barring other priorities we expect to complete the work
Outside of CAV control
OTHER ROADMAP ITEMS | PROJECT | PLANNED Q1 SUBJECT TO RESOURCE | UPDATES ON Q1 PLANNED WORK
| Sustainable funding plan for D&HI |  | Joint work has started with finance on this. Cyber team has been funded. Business cases pending for other resource requirements. | Going off track | Some BC funded, others still to be funded
| Virtual Hospital & virtual inpatient wards | Resolve data issue | BIS team successfuly identified and got agreed a solution to data issue (we are not the only organisation to have this issue). A 2nd iteration requiring some additional development work is planned. as well as resolving the data issue, this enables a new 'virtual hospital' meaning a capability has been delivered, not just a point solution. How to optimise this is being considered by Ops Directors - the benefit of this work is that it should enable flow i.e. discharge from a bed but still manage the patient virtually (where appropriate). Patients can recover in their own home whilst still attending the hospitakl for teratments, diagnostics, monitoring as required. | Going off track | Lack of resource - work has been prioritised
| E-whiteboard ED to ALL specialties | Already completed for ED to medicine referrals. Do the work to extend this to SDEC and then all specialties. | Planning work underway to make this available to all specialties to concide with SDEC Phase 2. Tracks patients, shows who is with the specialty, who is due a review, the status of relevant senior review through to discharge or admittance. Supports improved patient care & reduced clinical risk through improved information flows and patient tracking. Positive feedback from Drs & releases clinical time | On track
| Welsh Nursing Care Record | National programme managed by CNIO with digital in support | Devices procured, planning underway to implement (led by nursing) - Carts & Laptop devices confirgured - carts due to be delivered in two weeks with a view to commence proof of concept in Barry Hosipital Mid July. Work still underway to configure iPads to work with Corporate Wifi | On track
| Scheduling - community nursing | Progressed rollout of Malinko across District Nursing Teams to 80% | Progress on target, supported by a temp implementation officer | On track
| e-triage business case - All Wales BC, with national UEC clinical lead | Arrange technical meeting and ED walkabout to inform business case | Technical meeting completed, ED walkbaout planned July. Questions over process to attract funding - in discussion with national policy lead UEC | On track
| Single sign on UEC | Project to be resourced |  | Off track | Lack of resource
| Link national e-advice solution with local e-advice solution | Both solutions live | Plan developed to integrate local with national solution which will mean a 4 day turnaround | On track
| (Wales) Emergency Care Dataset (replacing EDDS) - requires SNOMED | National Heads of Information are developing this. Milestones to be developed.
| Internal interoperability between major PAS (acute, community/MH and others) | Internal discussions on tactical solutions for individual use cases | Requires resource | Off track | Lack of resource
| Data gateway to enable Powerapps to consume PAS data | CAV build to facilitate this has been completed | In discussions with national O365 centre of excellence team to enable this | Off track | As update
| Signals for Noise | No milestone this quarter
| O365 capabilities | Archive file migrations underway | Pending resource to exploit | On track
| O365 licences for all CAV staff (prevously c2K shortfall) | Work has been done to idnetify licence sthat can be reused e.g. leavers | Pending national contract renewal | On track
| Data strategy |  | Output of Enterprise architecture work. CCIO will lead data strategy | On track
| Technical plan (EA, SA, TA plans) | Enterprise architecture to be developed and will infom | Exploring how this work could be achieved | On track
| Use your own device | Internal discussions on options
| Upskilling staff (generally in digital in CAV) | Update/develop inhouse training materilas for EUWS, E-whiteboard; etr radiology | Training materials refreshed for inhouse applications; radiology app materilas being developed | On track
| WICIS (critical care national application) | Due to be implemented Summer 2023 | Detailed fotprint surveys undertaken, equipment trials underway. National programme pushed back from 2022 to 2023 implementation | On track
COMPLETED 21/22 | PROJECT | WHAT IT DOES
| E-whiteboard for referrals ED to Medicine | Tracks patients, shows who is with the specialty, who is due a review, senior, some diagnosis and other information and outcomes. Patient safety improvement and now provides data that can be reused
| Electronic test requesting - blood (using WCP) | A national initiative supported by LINC funding via WG - compliance is high
| Virtual inpatients UEC | Enable patients who are stable to be maintained by ED staff in their own home e.g. overnight. Better patient experience
| Telephone advice & guidance | Reduces referrals by enabling phone consult between departments. ED now use this for referral discussions with SDEC
| Virtual consultations | CAV performing well against comparators yet in line with general decline nationally; now part of outpatients transofrmation programme and as part of other initiaves such as virtual village aim is to increase this activity further
| Windows 10 upgrade | Major programme
| Ivanti service desk | New service desk tool went live June. Will continuously improve and will become the equivalent to a front door for the digital service
| At Home (virtual ward) function | The ability to show patients are still under our care but that they are waiting At Home e.g. until the next day before coming in for further assessment or diagnostic. Much better experience for patients and reduces people numbers in ED / Paeds EU / SDEC when they don't need to physically be there
| RATZ notes of episode of care | Tracks patient thro RATZ, indicates to anyone reviewing patient they have been thro RATZ - notes can follow patient
| Safari round | Surfaces patients needing a review with their locations
| WIFI phones | infrastructure has been upgraded - removes the need to stay by the phone after you have bleeped someone as you can carry a phone around in your pocket
| Huddle report dashboard for ED | c50% of the information collected on status exists as a data point - a BIS dashboard has been produced to show these in near real time saving clinical time and improving
| Digitise perioperative care (epoac) | Pre-operative assessments were paper based, now moved to a digital solution developed inhouse saving clinical time
| Patient facing content | 20 leafelts completed by year end, work started on 336 however clinical time unavailable, plan and templates etc with comms team - no further reporting by D&HI