|  | Priority area(s) |
| --- | --- |
| Key focus should be on delivering | Regular monthly reporting of ‘Pathways of Care’ (DTOC) to be introduced for 2023-24 and reduction in backlog of delayed transfers through early joint discharge planning and coordination Replicate each specific priority area featured above. UHB Aim: Continue and improve partnership working to reduce DTOCs and ensure people are provided care in the most appropriate location for their needs |
| Baseline | Number of DTOC as January 2023 – 286 |
| Quarter 1: |  |
| - Milestones | 10% reduction in DTOC against baseline |
| - Actions | - Develop agreed pathways across health system aligned to demand. Multi-professional team leading on mapping to align capacity with demand - Improve referral processes to ensure we have accurate information to inform decisions - Weekly review of top 20 delays with agreed actions and output leading to increase discharges - Introduction of additional “Lakeside” capacity to reduce reliance on acute inpatient beds. - Sign of revised clinical model and workforce model for “Lakeside” |
| Quarter 2: |  |
| - Milestones | Maintain 10% reduction in DTOC against baseline |
| - Actions | - Develop plan for equivalent of “Lakeside” in Llandough footprint - Introduce trusted assessor role to support earlier patient review and work-up for discharge – supporting discharge to assess model - Demand and capacity modelling to be undertaken for CRT/VCRS as part of intermediate care plans in anticipation of upstream and step-up support for population - Develop cluster MDT to capture at risk patients, to include social and housing issues leading to early intervention and avoidance of admission |
| Quarter 3: |  |
| - Milestones | Maintain 10% reduction in DTOC against baseline |
| - Actions | - Introduction of “Lakeside” model in Llandough in anticipation of Winter. - Introduce geriatric outreach model (first phase) to support local nursing homes and avoid inappropriate admissions into the acute setting - Run “shared lives” business model for patients in Mental Health services to reduce CHC requirements. - Agree joint plan with local authority to increase care home % utilisation against beds available. |
| Quarter4: |  |
| - Milestones | Maintain 10% reduction in DTOC against baseline |
| - Actions | - Implementation and delivery of winter plan actions |
| Risks | - Workforce & resource within local authorities - Increased demand due to age profile and frailty of population - Sharing of information between health and social care Mitigations and approach - Developing agreed models of care based on population needs with focus on community and independent living - Partnership working on workforce models to alleviate constraints |
| Outcomes | - Decrease in the number of patients assessed for long term care in acute hospital setting - Increase in the number of patients able to access an appropriate Discharge to Assess pathway. - Earlier identification of social constraints both in community care setting and hospital to promote alternative care stream - Improved discharge back to independent living - Clarity around pathways to access most appropriate care leading to improved morbidity and mortality |
| Alignment with workforce plans | - Medical and clinical review of workforce for “Lakeside” - Review agreed workforce models and standardise streams for patients needing out of hospital care - Introduce Band 4 clinical roles reducing reliance on registrants - Develop primary care GP provision to support alternative services - Reduce requirement for premium workforce costs - Introduce trusted assessors if unable to appoint social workers |
| Alignment with Financial plans | - Revised model of care for “Lakeside” (integrated assessment care unit) – reduced cost - Align model with reduction of acute beds supported through alternative services developed in community care |