|  | Priority area(s) |
| --- | --- |
| Key focus should be on delivering | Reduction in backlog of patients waiting over 62 days to enable delivery of 75% of patients starting their first definitive cancer treatment 62 days from point of suspicion Implement the agreed national cancer pathways within the national target – demonstrating annual improvement toward achieving target by March 2026. |
|  | UHB Aim: Transform cancer services to reduce waiting times and improve outcomes for patients. |
| Baseline | Predicted baseline as at April 23: - SCP performance will be at 65% National Cancer Pathway working group being established |
| Quarter 1: |  |
| - Milestones | Achieve >75% compliance with the SCP standard Develop draft UHB strategy to deliver national cancer pathways Refreshed baseline assessment against compliance with national pathways |
| - Actions | - Maintain weekly oversight meeting - Improved compliance with internal standards: 14 days for first contact, day 28 for diagnosis and 10-day turnaround for rad/path - Maintain <10 over 104-day cohort - Implement agreed actions from tertiary pathway summit from Q4 22/23 - Targeted improvement to high volume pathways urology, lower GI, Upper GI, gynae - Re-format weekly PTL meeting with specialities - Agree approach to national cancer pathways and baseline with cancer stakeholder reference group. - Seek sign off from Executive Cancer Board. |
| Quarter 2: |  |
| - Milestones | Maintain >75% SCP compliance Complete gap analysis for national cancer pathway |
| - Actions | - Maintain weekly oversight meeting - Compliance with internal standards: 14 days for first contact, day 28 for diagnosis and 10-day turnaround for rad/path - Improvement trajectory for reducing >80-day cohort - Implement pathway changes for key volume specialities - Implement agreed actions from tertiary pathway summit from Q4 22/23 |
| Quarter 3: |  |
| - Milestones | Achieve >80% compliance with the SCP standard Tumour site priorities agreed in line with UHB cancer improvement plan and gap analysis. |
| - Actions | - Maintain Compliance with internal standards: 14 days for first contact, day 28 for diagnosis and 10-day turnaround for rad/path - Undertake refresh of tumour site demand/capacity (gynae, breast, UGI, LGI, skin, urology) - Delivery against improvement trajectory for reducing >80-day cohort |
| Quarter4: |  |
| - Milestones | Maintain >80% compliance with SPC |
| - Actions | - Maintain Compliance with internal standards: 14 days for first contact, day 28 for diagnosis and 10-day turnaround for rad/path - Delivery of improvement trajectory >62-day cohort |
| Risks | - Demand increase for cancer services > available capacity - Workforce availability - Timeliness of referrals into tertiary services - Future Industrial action - Clinical agreement on adoption of national optimal pathways |
| Outcomes | - Increase in number of treatments undertaken per month - Improved delivery against the 28-diagnosis standard – improved patient experience - Reduced waiting times for those with confirmed cancer to commence definitive treatment |
| Alignment with workforce plans | - Speciality specific workforce plans to be included in individual Clinical Board IMTPs highlighting areas of risk - Focus on priority areas: diagnostics (radiology, endoscopy, pathology) and theatres as critical enablers |
| Alignment with Financial plans | - Speciality specific financial plans to be included in individual Clinical Board IMTPs highlighting areas of risk - Focus on priority areas: diagnostics (radiology, endoscopy, pathology) and theatres as critical enablers |