|  | Priority area(s) |
| --- | --- |
| Key focus should be on delivering | Recover waiting time performance to performance framework standards for all age LPMHSS assessment and intervention and Specialist CAMHS. |
|  | UHB Aim: Maintain performance levels and continue to improve mental health services |
| Baseline | Children and Young People: Expected performance at April 2023: Part 1a – >90% Part 1b – 50% - children & 90% - adult SCAMHS (28 days to assessment) – 90% SCAMHS Intervention (no national target) – 55 weeks |
| Quarter 1: |  |
| - Milestones | Children: - Maintain compliance against Part 1a of MHM - > 80% - Maintain compliance for SCAMHS assessment delivered with 28 days - > 80% - Children: Maintain performance against Part 1b of MHM and SCAMHS intervention wait whilst reducing longest wait and volume of waiting list Adult: - Maintain compliance against part 1a and 1b |
| - Actions | Children: - Mobilise and embed new service structure and pathway model of delivery - Review and monitor DEMCAP - Clear job planning - Review and monitor patient flow through new model - Maintain staffing levels – recruit accordingly Adult: - Development of a single point of routine access for referrals to CMHT (pilot). This will indicate the viability of further roll out across Cardiff |
| Quarter 2: |  |
| - Milestones | Children: - Maintain compliance against Part 1a of MHM - > 80% - Maintain compliance for SCAMHS assessment delivered with 28 days - > 80% - Improve performance against Part 1b of MHM by 10% - Reduce SCAMHS Intervention longest wait to no longer than 24 weeks Adult: - Adult: Maintain compliance against part 1a and 1b |
| - Actions | Children: - Review and monitor DEMCAP - Clear job planning in line with DEMCAP and patient flow - Maintain staffing levels – recruit accordingly Adult - Evaluation of single point of routine access (SPOA) pilots and if effective begin next stage of roll out |
| Quarter 3: |  |
| - Milestones | Children: - Maintain compliance against Part 1a of MHM - > 80% - Maintain compliance for SCAMHS assessment delivered with 28 days - > 80% - Improve performance against Part 1b of MHM by further 10% - Reduce SCAMHS Intervention longest wait to no longer than 12 weeks Adult: - Maintain compliance against part 1a and 1b |
| - Actions | Children: - Review and monitor DEMCAP - Clear job planning in line with DEMCAP and patient flow - Maintain staffing levels – recruit accordingly |
| Quarter4: |  |
| - Milestones | Children: - Maintain compliance against Part 1a of MHM - > 80% - Maintain compliance for SCAMHS assessment delivered with 28 days - > 80% - Achieve compliance against Part 1b of MHM - > 80% - Reduce SCAMHS Intervention longest wait to no longer than 6 weeks Adult: Maintain compliance against part 1a and 1b |
| - Actions | - Review and monitor DEMCAP - Clear job planning in line with DEMCAP and patient flow - Maintain staffing levels – recruit accordingly |
| Risks | Children: - Existing backlog of patients waiting for intervention - Increasing demand and acuity of patient need - Recruitment and retention challenges – national shortage of staff across all MH professions Adult: - Unknown demand with 111 press 2 and cost of living impact - Workforce challenges – particularly at Band 6 |
| Outcomes | - Compliance against Part 1a and Part 1b of the MHM achieved and maintained - Improved access times for SCAMHS assessment and intervention - Timely access to care for people requiring support for emotional wellbeing and mental health support - Right place right time care through SPOA |
| Alignment with workforce plans | - National HEIW Workforce strategy for Mental Health |
| Alignment with Financial plans | - Core budget – recurrently funded through WG transformation money - Additional funding opportunities through possible WG transformation funding - SIF funding for SPOA roll out |