How will we measure our success – People and Culture Plan

| Key Area of focus | Actions we will take | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| --- | --- | --- | --- | --- | --- |
| Attract & Recruit | - Continue the streamlining of processes and efficiencies within the Staff Bank and increase the number and range of temporary staff to reduce agency spend. - Further increase the recruitment of staff from more diverse groups to reflect the local population (Prince’s Trust, Project search, Mosques etc.). - Continue to promote Cardiff and Vale UHB as the employer of choice by holding Careers events and close liaison with schools, universities, DWP and many other organisations. - Being responsive to changes in the service capacity to ensure the appropriate staff can be recruited and deployed to cope with changes in demand. - Reduce number of permanent vacancies. - Improve length of time it takes to recruit people into the HB. - Improve our ability to deploy our people in an appropriate way. | - Reduce time to shortlist to 7.5 days. - Cease HCSW agency usage by April 23 & improve supply on the Staff Bank to 85% & focus on substantive recruitment. - Implement Safecare onto all Acute wards by 04/23. | - Reduce vacancies to 9% - Reduce time to shortlist to 7 days - Maintain zero HCSW agency position - Implement Healthroster for Nursing workforce by 09/23. - Implement HealthRoster for Pharmacy by 09/23. | - Maintain time to shortlist at 7 days. - Maintain zero HCSW agency position. - Implement HealthRoster for Facilities by 12/23. | - Reduce vacancies to 8% - Maintain time to shortlist at 7 days. - Maintain zero HCSW agency position - Expand apprenticeship academy to incorporate new apprenticeship roles. - Commence implementation of HealthRoster for AHPs. - Commence implementation of e-rostering for M&D workforce. |
| Retaining our People | - Reduce turnover to a more sustainable position. - Promote and embed retention initiatives via a retention toolkit for managers. - Implement Wagestream for staff on e-rostering systems. - Development of bespoke OD interventions to support effective team performance and create high performing teams. | - Reduce the turnover in staff groups that are over 10% to a more sustainable position of 8-9%. - Continue to enhance the use of cultural surveys, stay and exit interviews, analysis the feedback & taking appropriate actions via development of an action plan. - Implement and promote Wagestream for staff on e-rostering systems. - Development of shortened VBA paperwork to support effective conversations. - Career clinics commenced to scope opportunities for staff wanting to transfer across the organisation. | - Reduce turnover to 12% - Develop more attractive flexible working options to support staff. - Implement and embed HEIW Retention Plan. - Implement and embed HEIW Self-assessment tool. - Implement HEIW health and care joint induction. - Deliver and promote a new Speaking up Safely Framework. | - Implement and embed WG preceptorship. | - Reduce turnover to 11% - Implement and embed HEIW AHP Retention Plan. |
| Wellbeing | - Agree and implement the Health and Wellbeing Strategy and Framework. - Improve wellbeing and reduce sickness absence to a more sustainable level, i.e. from 7% to 6%. - Reduce number of staff on long term sickness absence. - Implementation and evaluation of interventions, including peer support, workshops and leadership development - Provide an effective and consistent means of supporting staff through difficult situations, e.g. investigations; Coroner’s Court | - Improved monitoring, evaluation and reporting of wellbeing services leading to improved staff experience - Developed staff members able to facilitate effective feedback and learning opportunities for all staff in an evidenced way. - Develop a culture of effective peer support through structured 1-2-1 wellbeing conversations and improved manager capability. Embedded holistic approach to address Health Inequity, Safety and Quality giving equal weight to patients, communities and staff. | - Integration of the new All Wales Occupational Health database. - Improved access to multi-Disciplinary learning opportunities facilitated by Schwartz Rounds. - Consistent approach to avoidable employee harm, supported by process review and access to support. | - Successful evaluation of collaborative Occupational Health working. - Instil a cycle of improvement through evaluation and review of wellbeing intervention. - Consistent and collaborative approach to supporting staff wellbeing around traumatic events. | - Improved staff wellbeing, including reduced absence. - Reduction in the number of staff on long term sick leave suffering with stress, anxiety, depression by 10%. - Evidenced improvements in wellbeing recognised by review of activity via Corporate Health Standards. |
| Equity, Inclusion & Welsh Language | - Achieve the priorities identified in the Strategic Equality Plan (SEP). - Strive to meet the Socio-Economic Duty. - Develop Anti-Racist Action Plan. - Achievement and sustainability of Welsh Language standards. - Review of the EHIA process - Development of networks and Employee Resource Groups - Continued focus on achievement and sustainability of the Welsh language Standards - Improving quality of demographic data and reporting. | - Develop and implement Anti-Racist Action Plan. - Embed the HEIW Welsh Language ‘awareness’ course into mandatory training. - Improve rate of provision of all EDI data to 40%. - Improved recruitment practices to include effective Welsh Language assessment and translation of documents. - Introduction of Health Inequity, Safety and Quality Framework. - Increased awareness of Welsh language skills of staff to enable effective workforce planning. | - Develop and implement the workforce actions in the LGBTQ+ Action Plan. - 60% of recruitment adverts & Job Descriptions translated into Welsh. - Improve rate of provision of all EDI data to 55%. - Stonewall WEI submission. - Review development of Employee Resource Groups. - Develop programme of work so support areas with implementation of Welsh Language Standards. - Enhanced confidence in development and use of Welsh language skills in the workplace through training and networks. | - 70% of recruitment adverts & Job Descriptions translated into Welsh. - Improve rate of provision of all EDI data to 70%. - Progress Anti-Racist Action Plan. - Collaboration to review effectiveness of EHIA paperwork and process. - Achievement of further Welsh language standard requirements through introduction of enhanced patient management systems. | - Improve rate of provision of all EDI data to 85%. - 80% of recruitment adverts & Job Descriptions translated into Welsh. - Review of Anti-Racist Action Plan and LGBTQ+ Action Plan. |
| Education, Culture and OD | - Improve engagement. - Use feedback and data to underpin workforce culture transformation actions. - Development of UHB Leadership Principles and review of development pathways to further support enhanced leadership capacity and capability - Embedding and further development of the coaching network to support a culture of coaching - Continued development of leadership alumni and peer networks - Focus on effective values-based appraisals, values-based recruitment and developing healthy working relationships - Developing an organisational approach to Talent Management and Succession Planning - Continued support for HCSW to develop into RNs through the UHB’s Novice to Nurse development pathway, AHP assistants developing towards registered OT/Physio roles. - Provide education to support the implementation of Assistant Practitioners in nursing. - Review and refine the UHB Nursing and Midwifery Preceptorship programmes and continuation of the Student Placement Experience Improvement plan - Launch UHB ‘Return to Registration’ pathway, enabling nurses and midwives to return to practice via the OSCE route. - Continue to enhance and develop digital learning pathways, including e-portfolios. | - Improve VBA compliance to 85% by 07/23. - All staff participate in an annual review that is high quality and effective. - Improved staff skills and awareness through improved statutory and mandatory training to 85% by 07/23. - Development of a coaching culture through continued coach development. - Improved Executive Team awareness around protected characteristics through introduction of mentoring relationships and listening and learning opportunities. - Consistent approach to cultural assessment to provide comparable cross-UHB data. - Effective OD Commissioning Model enabling value added outcomes. | - Enhanced development opportunities through enhanced coaching network capacity. - Improved clarity and understanding of leadership behaviours, skills and knowledge through UHB Leadership Principles and development pathways. More outcomes in the sections rather than narrative. - Improved staffing profile and patient care due to new models of working and development pathways. | - Established and reviewed succession plans and talent pipelines for senior leaders. - Increased UHB awareness of staff engagement and experience through effective analysis and communication of NHS Wales Staff Survey. - Provision of excellent leadership and management development enabled through regular review and benchmarking. | - Embedded culture of review and improvement in education, culture and OD practices and programmes. - Improved staff experiences through learning and actions aligned to Anti-Racist Action Plan. - Organisational understanding of Staff Survey results and role in response. - Improved student placement experience and increased student placement applications. |
| Shaping our Future Workforce (theme 1,7) | - Change workforce models to meet the needs of our patients and population. - Introduce new and extended roles, review skill mix, etc. - Increase organisational capacity and capabilities in workforce planning, train approx. 100 managers/leaders in 23/24. - Robust workforce plans will support build a sustainable workforce by: - Improving retention & engagement - reducing reliance on agency - talent management - changing shape of workforce - improved quality & performance indicators. People Analytics - Ensure our workforce data is accurate, meaningful and accessible to assist with strategic decision making by 23/24. Moving from workforce reporting to people analytics. | - Recruit & train approx. 30 Assistant Practitioners, ward areas. - Continue to embed Physician Associates & secure a funding stream for the role. - Train 25 managers/leaders in workforce planning. - Agree priority areas for WP. - Design training plan for ESR users. - Work alongside e-Rostering team, ensure nursing staff records are attached to the correct wards in ESR. - Enhance data reporting by using Analytics software. | - Recruit & train an additional approx. 30 Assistant Practitioner, ward areas. - Train an additional 25 managers/leaders in workforce planning. - Provide training for managers and users in the correct use of ESR. - Extend People Analytics team capacity in reporting, in order to support resourcing, EDI, wellbeing and people planning initiatives. | - Recruit & train an additional approx. 30 Assistant Practitioner, ward areas. - Train an additional 25 managers/leaders in workforce planning. - Provide targeted training for managers in use and interpretation of staffing analytics reports as provided via SharePoint. | - Recruit & train an additional approx. 30 Assistant Practitioner, ward areas. - Train an additional 25 managers/leaders in workforce planning. - Introduce Anaesthetic Associates into workforce modelling. |