## Slide 1: 2022-2025 Cardiff and Vale Integrated Medium Term Plan
Update: Quarter Four

## Slide 2
PRIMARY CARE
TARGET FOR LAST QUARTER
ACHIEVED TARGETS
TARGET FOR NEXT QUARTER
FURTHER READING
Increase dental activity to 88% of pre-covid
Develop additional UPCC capacity in other Cardiff Localities – Cardiff North Pilot to go live in February.
Continue planning for Vale UPCC
Improvement of diabetes performance measures in line with WG targets
Identify and confirm the governance arrangements in which PCPGs will operate and consider PCPGs plans in light of the RPB Area Plan due to be published in Q1 23/24. Professional Collaborative further establish themselves and start to integrate into Cluster meetings structures.
Did not achieve pre-covid target of 88% - February equally 68% so a maintenance of Q3 performance. Achieving revised dental performance measures forms part of 2023/24 IMTP commitments
UPCC went live in Cardiff North – over 75% of C&V now have direct access to a UPCC with the remaining practices able to request access as needed.
UPCC changes in the Vale and in progress for Barry hospital.
Improved diabetes performance (% patients received all 8 NICE recommended care processes) from 33% to 43%.
Work continues on aligning planning and governance arrangements. PCPG meetings established. Links with Senior Leadership Group to be developed.
Ambitions as per annual plan:
80% appointment utilisation in UPCCs
Home Visit (P2) face 2 face in 2 hrs >90%
>90% of all eligible community pharmacies providing CCPS
>95% of practices reporting escalation levels
>90% of eligible practices offering Clinical Community Optometry Services (CCOS)
[Insert any additional documents here]
RISKS AND MITIGATIONS
Risks
Sustained and exceptional pressure on primary care, community teams and partner organisations
Dental access and increasing activity levels – staff sickness/vacancies, patient complexity, new contract has created new requirements incl. a change in IT software/
Mitigations
Continued escalation and close partnership working
SEE SLIDE 5,6,7,8 IN BASELINE DOCUMENT

## Slide 3
MENTAL HEALTH
TARGET FOR LAST QUARTER
ACHIEVED TARGETS
TARGET FOR NEXT QUARTER
FURTHER READING
Maintain Part 1a & 1b CYP and Adult targets
Improvement in Eating Disorder access times – reduction in waiting time to 9 months longest wait
Develop repatriation plan for delivery of trauma informed care services close to home
Deliver sustained improvement trajectory for neurodevelopment assessments
Go live with sanctuary provision for crisis care in adults
Go live with NHS 111 Press 2
Achieved >90% in adults and CAMHS for Part 1a. Achieved part 1b in adults. Challenges in part 1b for CAMHS – not achieved.
Achieved - March 23 max wait = 24 weeks adult & 5 weeks paeds
Trauma informed care services plan delivered – not achieved but planned for next year
Neurodevelopment – overall decline in waiting list since Sept 2022 but significant waits remain
Sanctuary – planned go-live in Q1 23/24
NHS 111 press 2 – go live achieved.
111 Press 2 advertised nationally and evaluated
Launch of Sanctuary
Reporting of all intensive psychological therapy waiting times
Part 1a and 1b compliance
Planning and Governance for New Roles in Mental Health Workforce
Neuropsychiatry - commence recruitment following WHSSC approval
WARRN replaces Form 4 risk assessment
Commencement of Royal College of Psychiatry (RCP) Review
RISKS AND MITIGATIONS
RISKS
Increasing demand into mental health services (CYP and adult) as compared to pre-covid
Increase in out of area placements due to pressures in inpatient MH system
Workforce recruitment and retention
MITIGATIONS
Increase support into tier 0 (website) and recovery college to get upstream of pre urgent and acute demand
Continue to develop innovate workforce solutions, for example peer support and work
SEE SLIDE [5,6,7] IN BASELINE DOCUMENT

## Slide 4
URGENT AND EMERGENCY CARE
TARGET FOR LAST QUARTER
ACHIEVED TARGETS
TARGET FOR NEXT QUARTER
FURTHER READING
Continue to deliver ambulance handover performance that makes every effort to minimise long delays
Deliver additional winter capacity – additional beds, social care capacity and SDEC/admission avoidance programmes to maintain hospital flow and performance
Develop plans to create a fit for purpose ED, assessment and SDEC areas
Develop plans for single point of access for paediatrics
Roll out the high-risk cohort approach to Cardiff North Cluster to prevent admission to hospital and promote home first approach
Go-live on next Cardiff UPCC
Continue to develop Vale UPCC future plans
Achieved – met ambulance handover commitment
Achieved – additional winter capacity delivered in conjunction with partners
Achieved – plan to enact acute site changes in Q1 23/24
Ongoing – plans for paeds SPOE in discussion
Ongoing – high risk cohort roll out planned for Q1 23/24
Achieved – UPCC went live in Cardiff
Achieved – UPCC vale plans in development
Maintain zero 4-hour ambulance handover delays
No patient waits >24-hour in ED
Reduce the number of delayed transfers of care patients by 10% on January ’23 baseline.
Cohort additional MFFD patients in Lakeside Wing
Reduce 21-day length of stay by 5% from Q1 2022 baseline
Reduction of ED majors’ attendances of 5% compared to same period 2022/23
10% increase in the total number of patients managed through SDEC
80% appointment utilisation in UPCCs
Home Visit (P2) f2f in 2 hrs >90%
Stroke – 70% patients scanned within 1 hour
Hip Fractures – 75% patients admitted to ward within 4 hours
RISKS AND MITIGATIONS
Risks
Sustained pressure across UEC pathways
Social care capacity challenges
Delayed discharges and increased length of stay
Long waits for admission and impact on patient experience
Significant workforce pressure across Health and Social Care
GMS Sustainability
Mitigations
Joint working across Health and Social Care – implementation of CEO led Incident Management Team approach
Ongoing workforce recruitment (locally, nationally, internationally) and focus on staff wellbeing
SEE SLIDE [5,6,7] IN BASELINE DOCUMENT

## Slide 5
OUR CONTINUED COVID-19 RESPONSE
TARGET FOR LAST QUARTER
ACHIEVED TARGETS
TARGET FOR NEXT QUARTER
FURTHER READING
Continue delivery of covid vaccination programme
Continue monitoring of new variants and responding as necessary
Continue delivery of antiviral and antibody treatments
Achieved – continue to deliver programme and have approved plans to reduce service as per national model for 2023/24
Achieved – regular updates provided
Achieved – adapting model as per national model to provide service by health board in 23/24 rather than all wales approach from 22/23
Continue delivery of covid vaccination programme
Continue monitoring of new variants and responding as necessary
Continue delivery of antiviral and antibody treatments
[Insert any additional documents here]
RISKS AND MITIGATIONS
Risks
Future peaks of covid demand
Impact of significant winter peak in respiratory demand due to reduced exposure and continued increased social interaction
Ability to balance future demands with the continued recovery of services
Reduced sensitivity of modelling and demand predictions (less testing)
Mitigations
Continue monitoring of covid demand through combination of public health and operational intelligence
Deliver winter plan to meet needs of covid and non-covid demand
Continued partnership working to deliver improvement across unscheduled care

## Slide 6
@HOME
TARGET FOR LAST QUARTER
ACHIEVED TARGETS
TARGET FOR NEXT QUARTER
FURTHER READING
To create a blueprint for integrated assessment and care planning, shared care records, workforce and OD with an action plan and timeline for implementing new ways of working
To finalise the comms and engagement materials and begin initial engagement with staff to raise awareness of the programme and to help shape the programme moving forward
To further develop the programme intelligence to understand and articulate the impact of the programme
Delivery against plans to support 6 Goals and +1000 beds initiatives
Align MDT work across all clusters to understand the delivery of similar approaches in the region
To develop a clear understanding of the interdependencies of the other major strategic programmes; SOFH, SOFCS, SOFW:IOC to begin to define future tranches of the programme
Initial workshops undertaken to begin development of a new target operating model; specifically focussed around integrated assessment and care planning, shared care records, workforce and OD.
First draft of comms and engagement materials developed including website, leaflet and filming underway. Plan for comms and engagement to raise awareness in development.
Impact data beginning to be monitored at regular programme boards
Shared data has also highlighted a high risk cohort of patients who would benefit from a proactive approach to management of needs to ensure they move through the system
Momentum and plans developing around delivery of programme activity to support the 6 Goals strategy; specifically around crisis response and MDT prevention
Initial discussions undertaken to map interdependencies between major strategic programmes
Further workshops to develop an action plan and timeline for implementing new ways of working in the locality, with plans developed around; assessments and care planning, shared care records, workforce and OD
Comms and engagement plan to begin rollout to promote and increase the profile of the @Home programme
To develop and refine delivery plans for the programme against ‘6 Goals’ with recognitions of ‘Further Faster’ to implement community transformation by winter 2023
Understand maturity of MDT work across all clusters to align reporting and to define ambition and understand resource requirements for rollout across the region
Crisis response intermediate care business case and delivery plan to be defined with a plan to secure resource
Programme board minutes from 23.01.23 and 08.03.23 are available via the programme manager, Chris Ball Christopher.ball@wales.nhs.uk
Regular status update reports to Strategic Portfolio Steering Group available
Note that this programme is a partnership programme and as such is Regional Partnership Board-led, with the CVUHB as a major partner. It is also one of the CVUHB’s strategic programmes
RISKS AND MITIGATIONS
RISKS
Lose momentum as the programme shifts from scoping to delivery
Failure to align with other major programmes (SOCS, Primary care transformation, Recovery, CC Ageing Well Strategy) and risk of gaps/duplication
Digital capability and maturity to support multi-agency integrated care model
Operational leadership capacity compromised due to ongoing pressures
Not securing cross-partnership agreement of the future TOM
Not defining clear benefits/metrics and interdependencies
Not including tapering of RIF funding over lifetime of the 5yr programme into organisational financial planning and not securing local funding to replace it.
Ability to create investment and growth in community, primary and social care services to deliver more activity and impact in out of hospital settings
MITIGATIONS
1. Clearly defined programme scope and deliverables with clear governance
2a. Close liaison with PCIC leads and programme directors
2b. Interdependencies mapping across key programmes
3. RPB-wide digital maturity programme to be established
4. Provide direct support and ensure programme supports operational priorities
5. Co-production of future TOM with org leads and seek agreement of execs
6. Alignment of organisational metrics to programme
7 and 8. Work with DOFs and service leads. Establishment of robust business cases with evidence of impact
SEE SLIDE [10] IN BASELINE DOCUMENT

## Slide 7
DIGITAL – Q4 UPDATE – slide 1 of 2
TARGET FOR LAST QUARTER
ACHIEVED TARGETS
TARGET FOR NEXT QUARTER
FURTHER READING
Digital Front Door - no milestone this quarter. Update provided on Q3 milestone SNOMED CT work scoped and planned
DSPP NHS Wales App – meetings between DSPP and suppliers
PROMS - Estimated - alignment with national PROMs ViH programme and target architecture
Shared health and care records using LDR – common demographics store
Outpatients transformation - application on PMS redesign tested and into Production
Rollout of WAP e-referral management within PARIS services (Community MH PCIC)
Digital dictation & Transcription re-procurement
Unplanned project STAMP in support of 6 Goals prioritized over other work in this area, all on track
Meeting being arranged by DSPP (national programme)
Not met – changes in DSCNs via national ViH team, CAV working closely with ViH team in support
Not met, unfunded by DPIF. RPB underspend has funded demographics link in TEST between PARIS and WDS, traversing LDR as a PoC
Delayed in favour of 6 Goals work – aiming for Q1 23/24
Resource constraints have delayed this work to Q1 - 90% complete
Delayed to June 2023, lack of capacity
See slide 2
N/A
RISKS AND MITIGATIONS
RISKS
Our main constraint in pace is limited by resource availability e.g. diverted to respond to operational needs
MITIGATIONS
Review and prioritisation means some activities have been paused, allowing us to move to a position where the majority of plans are on track
A digital advisory board to be established to ensure digital resource is sequenced to organisational programme and project priorities
Assessment of capacity undertaken, there are some resource gaps (difficulty recruiting the right skills and expertise which is a wider challenge than just for this UHB)
SEE SLIDE [9] IN BASELINE DOCUMENT

## Slide 8
DIGITAL – Q4 UPDATE – slide 2 of 2
TARGET FOR LAST QUARTER
ACHIEVED TARGETS
TARGET FOR NEXT QUARTER
FURTHER READING
eTR pathology - understand DHCW roadmap / look at local interim options
Clinical/specialty applications - Internal referrals work extended to all appropriate specialties
Interoperability - PMS & PARIS interoperability in test
Scan4Safety - Implementation in line with plan agreed Q4 2021/22
WCP requires work from DHCW who are working with CAV. GP radiology live, acute
Go Live etr radiology inpatients and UEC final pilot starts 03/05 and is already supporting c1,800 requests per week which is a success
Displaced by major application implementations e.g. WNCR, ePMA
Progressing slowly WER as dedicated resource contract ended March
There have been delays due to programme resource constraints, good progress made by cardiology
Major infrastructure projects - Install and Configuration
Wales critical care information system (national programme) - Procure relevant infrastructure to support implementation. Clinical UAT of application
WNCR (National application) - UHB Wide implementation
UHW2 Digital SoC for SMART healthcare system – receive funding from WG, recruit resource; Research, Gathering intelligence & expertise
Scan4Safety (National programme) - Cardiology Live; WiFi in all upcoming areas; complete stock audit SSU and SSSU ready for Go Live
ePMA (National programme) - Procurement complete, Contract awarded to provider, WG bid for hardware, software & implementation team
Common demographics store - Demographics Architecture documented and processes drafted
PROMS – complete integrations, recruit, onboard new services, PROMS FIHR repository in place
N/A
RISKS AND MITIGATIONS
RISKS
Main constraint in pace is limited by resource availability which is diverted to meeting organisational priorities and operational needs
MITIGATIONS
Review and prioritisation means some activities have been paused, allowing us to move to a position where the majority of plans are on track
A digital advisory board to be established to ensure digital resource is sequenced to organisational programme and project priorities
Assessment of capacity undertaken, there are some resource gaps (difficulty recruiting the right skills and expertise which is a wider challenge than just for this UHB)
SEE SLIDE [9] IN BASELINE DOCUMENT

## Slide 9
OUR PHYSICAL INFASTRUCTURE – MAJOR CAPITAL SCHEMES
TARGET FOR LAST QUARTER
ACHIEVED TARGETS
TARGET FOR NEXT QUARTER
FURTHER READING
MAJOR CAPITAL SCHEMES IN CONSTRUCTION: OUR ACUTE INFRASTRUCTURE PROGRAMME
Genomics – FBC approved by WG – Formal approval 07/09/2021; Continued work on site
UHL Engineering Infrastructure - Funding approved by WG 05/10/2021 Continued work on site
UHL Endoscopy Expansion – BJC approved by WG –18/01/2022 formal approval Continued work on site
MAJOR CAPITAL BUSINESS CASES IN DEVELOPMENT: OUR ACUTE INFRASTRUCTURE PROGRAMME
Hybrid/Vascular & Major Trauma Theatre – OBC approved – 21/01/2022; FBC in development and submission to WG planned – Q3 2022; Total cost est: £33.5m
UHL – CAVOC theatres -SOC approved 25/03/2021 – approval of fees 16/12/2021; OBC in development and submission to WG planned – Q3 2022; Total cost est: £11.8m
Dental Block Main Electrical Distribution Replacement – In house design progressing from Jan 2022 to inform BJC for submission in 2022 –23
UHW Tertiary Tower Electrical infrastructure - BJC due for submission to Board Q1 2022; Total cost est: £2.2m
UHW Lift Refurbishment Programme - BJC due for submission to Board Q1 2022, Survey works commenced, Total Cost est: TBC
Mortuary Refurbishment - Carried forward from 2021-22 , BJC in development, Total cost est: £2m
MAJOR CAPITAL SCHEMES IN CONSTRUCTION: OUR ACUTE INFRASTRUCTURE PROGRAMME
Genomics construction commenced
UHL Infrastructure Construction Commenced
UHL Endoscopy Construction Commenced
Adult Fracture Clinic UHW Commence Construction
MAJOR CAPITAL BUSINESS CASES IN DEVELOPMENT: OUR ACUTE INFRASTRUCTURE PROGRAMME
Hybrid/Vascular & MTC FBC submitted to Welsh Government
UHL CAVOC Theatres OBC paperwork completed
UHW Tertiary Tower Electrical infrastructure – sent to Board
UHW Lift Refurbishment Programme - BJC paperwork completed
Mortuary Refurbishment Programme - BJC paperwork completed
MAJOR CAPITAL SCHEMES IN CONSTRUCTION: OUR ACUTE INFRASTRUCTURE PROGRAMME
Adult Fracture Clinic UHW Construction to be Completed
Genomics Construction Completion
MAJOR CAPITAL BUSINESS CASES IN DEVELOPMENT: OUR ACUTE INFRASTRUCTURE PROGRAMME
UHL CAVOC Theatres submit OBC to Board May
UHW Lift Refurbishment Programme submit BJC to Board
Mortuary Refurbishment Programme submit BJC to Board
BMT SOC development for submission to Board July
Hybrid/Vascular & MTC FBC Welsh Government Approval
UHW Tertiary Tower Electrical infrastructure – submitted to Welsh Government
Acute Infrastructure and Integrated Ward Moves UHW site – Production of design programme and estimates
[Insert any additional documents here]
RISKS AND MITIGATIONS
SEE SLIDE [13 - 15] IN BASELINE DOCUMENT

## Slide 10
OUR PHYSICAL INFASTRUCTURE – COMMUNITY
TARGET FOR LAST QUARTER
ACHIEVED TARGETS
TARGET FOR NEXT QUARTER
FURTHER READING
MAJOR CAPITAL SCHEMES IN CONSTRUCTION: IN OUR COMMUNITY
Maelfa Wellbeing Hub completed and in use
MAJOR CAPITAL BUSINESS CASES IN DEVELOPMENT: IN OUR COMMUNITY
Wellbeing Hub Ely (Park View) OBC submitted complete scrutiny questions
SARC - Regional Hub OBC submitted to Board, awaiting approval for FBC development
Health & Wellbeing Centre – CRI OBC submitted to Board, Welsh Government scrutiny process completed
Wellbeing Hub Penarth
MAJOR CAPITAL SCHEMES IN CONSTRUCTION: IN OUR COMMUNITY
Maelfa Wellbeing Hub completed and in use
MAJOR CAPITAL BUSINESS CASES IN DEVELOPMENT: IN OUR COMMUNITY
Wellbeing Hub Ely (Park View) OBC submitted to Welsh Government
SARC - Regional Hub OBC submitted to Board, Welsh Government scrutiny completed awaiting approval for FBC development
Health & Wellbeing Centre – CRI OBC submitted to Board, Welsh Government scrutiny process commenced
Wellbeing Hub Ely (Park View) OBC Welsh Government Approval
SARC - Regional Hub OBC Welsh Government Approval
Health & Wellbeing Centre – CRI OBC submitted to Board, Welsh Government scrutiny process completed
Wellbeing Hub Penarth commencement of OBC refresh
[Insert any additional documents here]
RISKS AND MITIGATIONS
Wellbeing Hub Penarth - Original scheme under review due to changing requirements of Local Authority
SEE SLIDE [13 - 15] IN BASELINE DOCUMENT

## Slide 11
PLANNED CARE
TARGET FOR LAST QUARTER
ACHIEVED TARGETS
TARGET FOR NEXT QUARTER
FURTHER READING
Continued improved in Cancer standards and reduction in backlog with ambition for 0>104 days
Ambition to eliminate > 3 year waits by March 23
Successful implementation of Vanguard Q4 plan with CTM and AB
Delivery of commitments against ministerial ambitions for March 23
Finalise D&C plans for all specialties for 23/24 Plan
Successful repatriation of fracture clinic from UHL (impact felt Q1)
A focus on theatres efficiency through newly established oversight group looking at workforce challenges, theatre booking, utilisation, resource allocation, and suite of metrics to track.
Focus on plans for neurodevelopment - expansion of the service is key to improve ADHD and autism management by applying a whole system pathway approach.
Cancer backlog reduced from 442 in April 22 to 244 in Mar 22. Over 104 day position improved from >200 to 57 at end of March including tertiary patients
End of March 62 day performance was over 60%
On track to over perform on 52 week new outpatient waits for end of December – IMTP modelled circa 17, 000 and End of March position 10102.
2192 > 104 new outpatients waits at end of March mainly in high volume surgical specialties and allergy
823 3 year waits in excess of trajectory, impacted on by industrial action
Weekly planned care performance meeting in place to track the 52 week outpatient cohort and ensure that it is reducing.
Mobile Eye Theatres remained in place through Q4 and in place for Q1 23/24
Mobile endoscopy continued and will be running 7/7. Activity across endoscopy is at 119% of pre-COVID activity
Orthopaedic productivity increase – theatre utilisation at 92% - exceeding some of GIRFT productivity measures
GIRFT support in Gynaecology has continued – the service is working through implementation of the workforce plans
Adult fracture clinic nearing completion with handover in Q1
8 week diagnostics target improvements: radiology 2168 at the end of march due to increasing support for cancer pathways and the emergency stream, Endoscopy: 1600 end of Nov 22 1565 at the end of March23
14 week Therapy improvement: 1209 In Nov 22 to 952 at the end of March
D+C modelling complete in all specialties for 23/24 plan
Work continues to improve access for neurodevelopmental services with waiting times still significantly long
Theatres oversight group established and theatres summit held sign up to ambitious productivity plan of working towards 95% session utilisation
>75% compliance with the 62-day SCP standard
Develop draft UHB strategy to deliver national cancer pathways
Undertake high impact evaluations of first three key specialities
New outpatients - 0 patients waiting longer than 52-weeks, excluding Allergy, Urology, Rheumatology, General Surgery, Urology, Ophthalmology, Orthopaedics and Spines
Total treatment – 0 patients waiting longer than 104-weeks excluding Gynaecology, General Surgery, Urology, ENT (adult and paeds), Ophthalmology and Spines.
Therapies - 0 patients waiting over 14 weeks (excluding audiology).
Co-produced Model of Care agreed, current services provision mapped, gap analysis complete
[Insert any additional documents here]
RISKS AND MITIGATIONS
RISKS
Impact of sustained system pressures on planned care (lack of beds and staffing)
Availability of workforce to run additional capacity
Availability of capital to enable transformational change
Ability to deliver national delivery ambitions in timescales
MITIGATIONS
Reviewing skills mix in delivery of planned care, working with insourcing companies where appropriate
Clear, prioritised and Exec supported site masterplan in place to support targeting of resources
Determined specialties where 52 week Op wait can be achieved and improvement plans in high volume specialties
SEE SLIDE [5,6,7] IN BASELINE DOCUMENT

## Slide 12
SHAPING OUR FUTURE POPULATION HEALTH
TARGET FOR LAST QUARTER
ACHIEVED TARGETS (END Q4)
TARGET FOR NEXT QUARTER
FURTHER READING
Vaccination and immunisation
Continue to provide 'mop up' Covid-19 and flu vaccinations to eligible groups across primary Care and the Mass Immunisation programme in accordance with WHC 2022_035.
Delivery of Spring Booster Covid-19 programme in line with national planning assumptions (pending JCVI recommendations)
Communications plan for the Amplifying Prevention programme (including immunisations) to be developed for different settings (e.g. schools, workforce, public).
Targeted actions with community, schools and workplaces in Cardiff and Vale as part of the Amplifying Prevention programme
Evaluation of TTP/Contact Tracing work to support uptake of Childhood Immunisations and potential expansion to an additional Cluster.
Delivery of polio catch up programme in line with WHC 2022/027 using a mixed delivery model
Development of UHB Vaccine Equity Strategy by end of February
Review the approach for tackling inequalities in vaccination uptake amongst ethnic minority communities.
Healthy weight: move more eat well
Development of local policies restricting High Fat Sugar Salt advertising/increasing healthier advertising across the UHB, Cardiff and the Vale of Glamorgan progressed through established working groups
Targeted action to improve whole school approaches to food underway.
Increase Food Cardiff membership to 250 individuals representing 100 organisations
Cardiff Sustainable Food Business network established with a minimum of 10 participating businesses
Vaccination and immunisation
'Mop-up' Covid-19 Autumn 2022 Booster and flu vaccinations delivered for eligible groups across Primary Care and the MVCs in line with WHC 2022_035. Over 163,000 Autumn 2022 Booster vaccinations delivered to Care Home residents, people aged 50 years and over, health & social care workers and those with clinical risk factors.
75% uptake target met for flu vaccine amongst people aged 65y and older.
Spring Booster programme being delivered from 1 April 2023 in line with JCVI advice.
Communications plan for the Amplifying Prevention programme (including immunisations) developed for different settings. Targeted actions underway with community, schools and workplaces in Cardiff and Vale as part of the Amplifying Prevention programme
A second round of calls made to families of 143 children in the South West cluster who were missing vaccinations. 115 successful calls, to date 18 children now vaccinated. A further 17 families were due to make appointments, these will be followed up. The polio vaccination catch up offer resulted in 29 children vaccinated, 65 DNA, 173 refusals and 24 not eligible
Draft Vaccine Equity Strategy developed. A revised partnership approach for tackling inequalities amongst ethnic minority communities agreed between the UHB and Cardiff and Vale Local Authorities.
Healthy weight: move more eat well
MMEW action relating to educational settings, workplaces and healthier advertising progressing as part of Amplifying Prevention approach.
Food related benefit digital training launched and shared nationally.
Working groups establishing to progress development of local policies restricting High Fat Sugar Salt advertising/increasing healthier advertising across the UHB, Cardiff and the Vale of Glamorgan.
Targeted action to improve whole school approaches to food underway. School clusters identified and event with senior school leaders took place (March).
Food partnerships have secured funding from Welsh Government for 23/24 to support the work of Food Cardiff and Food Vale.
To report on an agreed subset of actions from the updated Local Public Health Plan for 2023-2026
[Insert any additional documents here]
RISKS AND MITIGATIONS
RISKS
MMEW - Availability of future data to track overarching project outcomes
Vaccination – childhood immunisation uptake is lower than national averages and declining in some areas (latest quarterly data Jan-Mar 2022)
Flu Vaccination – several factors (including co-administration and concern about co-infection) may lead to increased demand for flu vaccine during 22/23 which may outstrip the supply.
MITIGATIONS
MMEW – improving surveillance for Healthy Weight - HWHW priority /concerns raised with PH Observatory/HWHW Surveillance Group
Vaccination – various work streams underway with Primary Care Clusters / GP Practices / local communities to increase uptake as well as communication/PR campaign.
Flu Vaccination – i) requesting information from GPs as to whether there are supply concerns. Ii) accessing a national/central supply of vaccine that will be available to all Health Boards if local supplies are depleted (tbc).
SEE SLIDE [16/17] IN BASELINE DOCUMENT

## Slide 13
SHAPING OUR FUTURE POPULATION HEALTH
TARGET FOR LAST QUARTER
ACHIEVED TARGETS (END Q4)
TARGET FOR NEXT QUARTER
FURTHER READING
Systematically tackle inequalities
Evidence of progress against revised Engagement Coordinator milestones
Delivery of agreed partnership action contained in amplifying prevention plan, including agreement of indicators
Increase routine alcohol screening in Primary and Secondary Care to identify hazardous and harmful drinking behaviours
Sustainable and healthy environment
Further Level 2 Charter organisations confirmed
Formal approval by C&V UHB to sign Level 2 Charter
Initiation of project to understand traffic impacts at UHW and UHL, including on air quality
Process and timescales for HE/FE Healthy Travel Charter development agreed
Systematically tackle inequalities
Research to feed the development of a new strategic framework for C&VUHB to tackle inequalities in health outcomes, harm, experience and access for the organisation has been completed and a meeting is planned for February with key stakeholders
Conversations with the Digital Team, Innovation Team, Public Health Wales and other partners to agree a measurement set to support the framework continue and indicators are being proposed
Multiagency Amplifying Prevention Delivery Board and its Operational subgroup has driven further community and workplace delivery, and developed an action plan for 2023/24
A revised partnership approach for tackling inequalities amongst ethnic minority communities agreed between the UHB and Cardiff and Vale Local Authorities.
Sustainable and healthy environment
Four signatories to Level 2 Charter now confirmed, additional organisations finalising governance arrangements prior to announcing. C&V UHB planning to formally sign in Q1 23/24
NO2 diffusion tubes placed at UHW and UHL following approval for project by SLB, monthly data starting to be recorded
Discussion with stakeholders regarding HE/FE Charter – early consensus seems to be set of principles about application of existing Charters would be more helpful, rather than whole new Charter
To report on an agreed subset of actions from the updated Local Public Health Plan for 2023-2026
Shaping our Future Population Health plan 22-25
Shaping our Future Population Health flash reports to Strategy and Delivery Committee
RISKS AND MITIGATIONS
RISKS
MITIGATIONS
SEE SLIDE [16/17] IN BASELINE DOCUMENT

## Slide 14
SHAPING OUR FUTURE POPULATION HEALTH
TARGET FOR LAST QUARTER
ACHIEVED TARGETS (END Q4)
TARGET FOR NEXT QUARTER
FURTHER READING
King’s Fund recommended programmes
Final King’s Fund report proposals to be considered at UHB Strategy and Delivery Committee and RPB
King's Fund to host a workshop with local partners
Priorities for implementation agreed with stakeholders
Tobacco
Continued implementation of an integrated ’Ottawa’ hospital smoking cessation programme reflecting nationally agreed priority actions to include systematic, routine recording of smoking status on admission, Brief Intervention advice and support to all smokers and referral to specialised smoking cessation services
On-going monitoring and review of MAMSS has resulted in an alternative delivery model being piloted for one year with an aim to increase longer term engagement (beyond initial advice and support) in order to increase numbers quitting smoking
Establish No Smoking Enforcement Officers at UHW and UHL reflecting a flexible delivery model to reduce smoking incidence at hospital sites
Actions to support a smoke-free environment for Mental Health patients to include sensitive enforcement options at UHL
King’s Fund recommended programmes
The two final King's fund reports on further strengthening prevention in primary care and developing an integrated health and care system, were well received by SLB, UHB Strategy and Delivery Committee and Cardiff and Vale RPB. Both organisational and RPB leaders have committed to attend the King's Fund facilitated workshop in June, and to use the reports to inform the UHB Strategy refresh and Area Plan update.
Tobacco (data for 2022-2023 not available currently)
The smoking prevalence rate for Cardiff and Vale of Glamorgan is 12% (NSW, 2021-2022), the same as the previous year and is one of the lowest rates in Wales
2.1% of smokers made a quit attempt 2021-2022, reflecting a static position from last year (2.2%)
64% of 'Treated smokers' quit smoking (self-reported) at 4 weeks, Qtr 3, 2022-2023, a decrease from 80%, Qtr 2, 2022-2023. 74% quit smoking (self-reported) 2021-2022
The hospital smoking cessation programme achieved an 85% 4 week quit rate (Quarter 3, 2022-2023) and a PGD has been agreed for provision of Nicotine Replacement Therapy (NRT) for patients on admission
42% of Community Pharmacies offer a Level 3 Enhanced Smoking Cessation Programme, 38% a Level 2. 68% of Level 3 services are located within areas of high deprivation
A MAMSS Programme was implemented in April 2021. 51% of pregnant smokers were referred to MAMSS, (Qtr 3, 2022-2023) – an increase from 25% pre-MAMSS. NRT provision available on first contact with a Midwife with 60% of MAMSS referrals accepting pharmacological support
No Smoking Enforcement Officer post implemented March 2022, to reduce incidence of smoking at hospital sites. Launch of ‘zero tolerance ‘ No Smoking Campaign, November 2022.
Mental Health Smoking Steering Group established to implement Smoke-free Regulations with progress on-going
To report on an agreed subset of actions from the updated Local Public Health Plan for 2023-2026
[Insert any additional documents here]
RISKS AND MITIGATIONS
RISKS
King’s Fund – further unanticipated delays encountered by the King's Fund. Revised delivery plan is for an initial slide-pack in mid Sept 2022, and full reports end Oct 2022
MITIGATIONS
King's Fund – further revised, phased plan will see full delivery by early Q3 2022/23
SEE SLIDE [16/17] IN BASELINE DOCUMENT

## Slide 15
QUALITY, SAFETY AND PATIENT EXPERIENCE
TARGET FOR LAST QUARTER
ACHIEVED TARGETS
TARGET FOR NEXT QUARTER
FURTHER READING
Priorities for ‘22
Establishment of the Organisational Learning Committee with themes identified and UHB wide improvements monitored
Establishment of the Clinical Safety Group
Psychological safety of staff
Human Factors awareness/investigations
What Matters to you questioning approach
The implementation and UHB wide rollout of the Once for Wales Patient Experience System
Establishment of the Organisational Readiness Group for the implementation of the Duty of Candour
Agreement of Mortality Indicators for all specialities
Clinical Safety Group established
Psychological safety of staff –Healthcare Support Unit commenced to support staff in inquests
Human Factors awareness/investigations –new investigation model for Nationally Reportable incidents to encompass contributory factors trialled in Clinical Boards
Implementation of AMAT-Clinical Audit System-Structured roll out commenced in Children and Women’s Clinical Board
Commenced use of the Once for Wales Patient Experience System
implementation of the Duty of Candour
Agreed use of Mortality Indicators for all specialities
Patient safety Review Tool (PSRT) developed and training programme developed and commencing in mental health May 23
Organisational Learning Committee will meet in Q2
Promote interactive sites for inquest support and Duty of Candour
A quality Summit is planned for quarter 1 with a follow up summit in Q2/Q3
Staff support Unit will roll out to support all staff
Data validation reviews as a focus for Duty of Candour work
Embedding the reporting framework in line with the Duty of Quality on going reporting methodology
Delivery and evaluation of PSRT educational programme
Commencement of Clinical Governance framework
Publication of clinical audit forward plan
Scoping for After Action Review Implementaion
Duty of Quality Sharepoint (https://nhswales365.sharepoint.com/sites/NXW_DOQ/SitePages/Supporting-Rsour.aspx)
Duty of Candour Information SharePoint
https://nhswales365.sharepoint.com/sites/CAV_Patient Experience/SitePages/Duty-of-Candour.aspx
RISKS AND MITIGATIONS
RISKS
On going Operational Pressures
IT infrastructure-Wifi availability across the UHB
Significant delays in recruitment
MITIGATIONS
Proportionate and prudent approach to Clinical Board involvement
Development of a recruitment plan to support implementation of the QSE Framework and IMTP
SEE SLIDE [4] IN BASELINE DOCUMENT

## Slide 16
WIDER REGIONAL WORKING WITH SOUTH EAST WALES PARTNERS
TARGET FOR LAST QUARTER
ACHIEVED TARGETS
TARGET FOR NEXT QUARTER
FURTHER READING
South East Wales Regional collaboration
Orthopaedics – Scoping work completed with regional consensus on the strategic direction of the programme. Early progress made on determining the viability (or not) of the HVLC interim hand and wrist service
Ophthalmology – Outstanding issues regarding the regional business case resolved with regional consensus and support for the service development agreed.
Diagnostics – Service specification agreed and formal procurement commenced regarding a preferred provider for the CDH project
Clarity regarding the strategic infrastructure development in CTMUHB (the Concorde project) and its relationship with the regional portfolio architecture.
CAVUHB / VNSHT partnership
Develop the project brief and deliverables for the haemato-oncology project, and receive approval from V@UHW Programme Board in February 2023.
Receive approval for the USC pathway internally from CAVUHB and VUNHST by the end of February 2023, and regionally via the Cancer Collaborative Leadership Group by the end of March 2023.
Develop the Strategic Outline Case for the new co-located BMT/haematology/AOS/CCRH unit by end of March 2023.
Stroke
Present proposal to the CHC National Service Change Board and develop local communication and engagement plan, in partnership with the CHC and third sector,
Complete demand and capacity work in partnership with colleagues from the National Stroke Board and the Delivery Unit.
Review outputs from the National Stroke Board workshop with colleagues locally at a stakeholder event by the end of March 2023, to explore options for a new regional clinical model.
South East Wales Regional collaboration
Orthopaedics – Finalised programme definition document and project plan for delivery of a proposed HVLC clinical model for delivery at the Llantrisant Health Park.
Ophthalmology – Business case for a 14 month interim regional cataract solution finalised and currently seeking local HB approval via respective governance routes.
Diagnostics – Service specification agreed and formal procurement commenced regarding a preferred provider for the CDH project
Stroke
The National Stroke Board has delayed submission of the service change pack until May 2023, as they continue to establish the case for change. Similarly a delay to the National Communication and Engagement framework (not yet received) has slowed regional progress in the development of our plan. A communication lead has been appointed, and project support secured, as the team build our regional plan, to be presented at the May Programme Board. EHIA completed and seldom-heard target groups identified.
Complete demand and capacity work in partnership with colleagues from the National Stroke Board and the Delivery Unit. Still not approved or shared - no timelines on when this is likely to happen.
Review outputs from the National Stroke Board workshop with colleagues locally at a stakeholder event by the end of March 2023, to explore options for a new regional clinical model. Still not approved or shared - no timelines on when this is likely to happen.
CAVUHB / VNHST partnership
Signed off at Velindre@UHW Programme Board February 2023 and scope agreed to review haemato-oncology services against capacity available at Velindre Cancer Centre.
USC pathway was not approved at February 2023 board due to clinical lead absence. Unsure on where Ash has got with this since Jon.
Develop the Strategic Outline Case for the new co-located BMT/haematology/AOS/CCRH unit by end of March 2023- Delayed until April 2023 due to the complexity of the case and substantial increase in the accommodation required.
South East Wales Regional collaboration
Orthopaedics – Planned clinical summit / workshop to develop HVLC clinical model.
Ophthalmology –
Subject to approved funding move into implementation phase of interim model
Start scoping of the long term sustainable solution for Q2 24/25 onwards
Diagnostics
Procure interim CDH solution at the LHP site
Scope clinical model for a regional endoscopy solution
Stroke
The National Stroke Board has delayed submission of the service change pack until May 2023 alongside , National Communication and Engagement framework (as above). Subject to issuing progress this agenda.
Complete demand and capacity work in partnership with colleagues from the National Stroke Board and the Delivery Unit.
explore options for a new regional clinical model- If possible given the outlined national context.
CAVUHB / VNHST partnership
Current programme manager has moved onto a new role. Successful recruitment has taken place with the new postholder stating summer ‘23.
RISKS AND MITIGATIONS
Resourcing and governance - Good progress has been made in filling key roles across the regional planning agenda whilst also putting in place key pieces of governance- however some gaps remain
Communications and Engagement- There is an immediate urgency to address the regions approach to communication and engagement. An analysis of regional capacity and capability has been undertaken which has noted a resource requirement of circa 100k per annum
Finance- Early scoping of all Programmes within this regional planning portfolio suggest there is a gap between the level of regional ambition on regional working and the likely level of resources available. This may likely result in the region having to make choices and prioritizations.
Digital- All regional Programmes of raising the issue of digital infrastructure as being a key enabler to effective regional working. There is a clear need to understand what the ‘must do’s’ are and also where immediate action can’t be taken what the effective ‘workarounds’ are so that regional working does not stall as a result.
Effective alignment between the Llantrisant Health Park programme and the wider regional planning agenda - There is a risk that the LHP does not develop the required close and meaningful relationships wit the wider regional planning agenda
National Programmes- There is a risk that the continued lack of clarity around the role and functions of some national level programmes slow progress of the regional agenda.
SEE SLIDE [17] IN BASELINE DOCUMENT

## Slide 17
SHAPING OUR FUTURE WORKFORCE
TARGET FOR LAST QUARTER
ACHIEVED TARGETS
TARGET FOR NEXT QUARTER
FURTHER READING
Over Q4 the People and Culture Team have continued to focus on the ‘Main Effort’ as part of the work to support the Winter Plan. The team have been aligned to the following UHB priorities and the People and Culture Plan:
Wellbeing (including cost of living)
Recruitment
Retention
Workforce Planning
In addition to these areas, the People Services Team have supported managers with operational matters, e.g. employee relations, terms & conditions.
Examples of achievements:
Work has continued to support staff with the cost of living crisis (e.g. roadshows, workshops, and a Task Group reporting into the Strategic Wellbeing group. SLB has approved the implementation of Wagestream, a financial wellbeing programme which aims to support financial resilience.
A draft Health and Wellbeing Strategy and Framework has been developed and is currently undergoing consultation.
Funding to maintain current establishment within Employee Wellbeing Services has been secured.
Following re-assessment, the UHB has retained both the Gold and Platinum Corporate Health Standards
84% of the required skill mix for IACU was recruited/deployed to support the winter capacity plan.
Since October 2022 180 HCSWs have been employed through the centralised recruitment processes.
Since July last year the TSD (bank) have recruited 472 HCSWs which enabled the UHB to cease the use of agency HSCWs, increase fill rates and reduce expenditure.
A retention toolkit has been developed for managers throughout the UHB to adapt to their own areas.
The CAVUHB Anti-Racist Plan has been developed through a co-production approach with colleagues from across the UHB
The rollout and implementation of HealthRoster is on track with 155 of 271 areas live
Two cohorts of Strategic Workforce Planning training took place in March 2023 with 23 leaders from Nursing, Allied Health Professionals and Management attending
A Band 4 Assistant Practitioner role has been developed to provide suitably trained staff to undertake care and interventions that fall between the HCSW and Registered Nurse role
Turnover rate trend is downwards since Apr-22; the rates have fallen from 13.66% in Nov-22 (the highest rate of turnover in the past 12 months) to 12.87% in Mar-23 UHB wide. This is a net 0.79% decrease, which equates roughly to 109 WTE fewer leavers. Sickness absence for March 2023 has reduced to pre-Covid19 levels.
The Statutory and Mandatory training compliance rate has risen, to 78.26% for March, 6.72% below the overall target. Compliance with Fire training has also risen during March, to 71.53%.
The trend of the rate of compliance with Values Based Appraisal has risen over the last 9 months; the compliance at March 2023 was 56.40%. (target 60%)
Reduce time to shortlist to 7.5 days.
Reduce the turnover in staff groups that are over 10% to a more sustainable position.
Continue to enhance the use of cultural surveys, stay and exit interviews, analysis the feedback & taking appropriate actions via development of an action plan.
Development of peer support facilitators and clinical leads (Schwartz Rounds).
Commence trial of peer support in identified Clinical Boards.
Introduction of Health Inequity, Safety and Quality Framework
Implementation of Anti-Racist Action Plan.
Embed the HEIW Welsh Language ‘awareness’ course into mandatory training.
Improve rate of provision of all EDI data to 40%.
Support UHB to improve VBA compliance to 85% by 07/23.
Support UHB to improve statutory and mandatory training to 85% by 07/23.
Cohort 2 of Assistant Practitioners to be ready to commence in July 2023.
Continue to embed Physician Associates & secure a funding stream for the role.
Introduce Anaesthetic Associates into workforce modelling.
Agree priority areas for strategic workforce planning .
Continue to focus on staff health and wellbeing – aim to further reduce sickness absence.
Continue to promote leadership and management development offerings.
The P&C Performance Report from March 2023 can be located in the Supporting Documents Folder in AdminControl and on the Cardiff and Vale UHB website.
The Workforce KPIs from March 2023 can be located in the Supporting Documents Folder in AdminControl and on the Cardiff and Vale UHB website.
RISKS AND MITIGATIONS
RISKS
Analysis of engagement results and feedback from wellbeing surveys has indicated low levels of staff morale, engagement and wellbeing.
Quality of patient care and experience, and team experience, may be impacted by turnover, absence, vacancies, high reliance on agency workers, etc.
The current climate has created a shortage of suitable candidates in many professions
Poor engagement caused by work pressures, staffing levels and cost of living crisis.
The possibility of further Industrial action remains.
rhiann
MITIGATIONS
P&C Team aligned to priorities and strategic programmes.
Effective partnership working with TU representatives.
Executive Performance Reviews with Clinical Boards.
Introduction of the People and Culture Committee in May 2023
SEE SLIDE [11,12] IN BASELINE DOCUMENT

## Slide 18
SHAPING OUR FUTURE CLINICAL SERVICES
TARGET FOR LAST QUARTER
ACHIEVED TARGETS
TARGET FOR NEXT QUARTER
FURTHER READING
Formal commencement of project 1
Completion of scoping for projects 2 & 3
Development of detailed resourcing plans for delivery of projects 2 & 3
Review of stakeholder mapping in development of wider communication and engagement plan for the strategic portfolio
Approval of patient involvement.co creation framework for the programme
Review of SOF hospitals Strategic Outline Case clinical component to be discussed with WG colleagues (inc. policy leads)
Project 1 commenced and progressing thought its first phase
Modelling and BI workstream established with agreed scope, deliverables and timelines
Scoping for projects 2 & 3 on hold due to limited resources being diverted to enable project 1 success
Stakeholder mapping completed
High level engagement plan drafted and approved by the strategic portfolio engagement and comms group
Meeting held with new WG policy lead and ongoing engagement meeting agreed.
Patient and Citizen involvement framework in draft for further development over the next quarter
-Learning framework in draft for further development in next quarter
Project board set up to oversee the CSP on behalf of programme board
Projections/plans and assumptions collated and approved by programme board
Approach and planning for Clinical Services chapter of the CSP complete and approved
Patient and citizen involvement framework completed
Learning system completed and embedded within programme
Involvement, Comms and Engagement workstream set up to oversee delivery of stakeholder engagement and comms plan.
Shaping Our Future Clinical Services - Shaping Our Future Wellbeing - Cardiff and Vale University Health Board - https://shapingourfuturewellbeing.com/shaping-our-future-clinical-services/
RISKS AND MITIGATIONS
Organisational capacity for strategic development during significant operational pressures
Organisational engagement with clinical strategy is not to the level required
Mitigations
Lessons learned undertaken and has informed future approach to enable most efficient use of time with teams
Work to refresh the organisations strategy Jan-Sept 23 will support engagement with future vision and set clear objectives for Clinical Services
Communications and engagement plan for strategic portfolio to be developed. Steering group established with key stakeholders in attendance.
SEE SLIDE [4] IN BASELINE DOCUMENT

## Slide 19
SHAPING OUR FUTURE HOSPITALS
TARGET FOR LAST QUARTER
ACHIEVED TARGETS
TARGET FOR NEXT QUARTER
FURTHER READING
Complete SOC scoping after receiving feedback from WG stakeholders to ensure the right content will be produced.
Agree ToR with WG for clinical review of model presented in PBC.
With a stable SOC scope, build a costed delivery plan (including what expertise should be recruited and what should be procured)
Seek PBC endorsement and funding to deliver SOC from WG
  Commence any procurement and internal recruitment exercises once funding commitment has been received.
Further development of Life Sciences Vision and actions with Cardiff University.
SOC scope approved by WG
ToR agreed with WG for the clinical review. A procurement was run by WG< but no bidders came forward. Steps are being taken to progress this matter by WG officials.
A delivery plan has been created for SOC. The resources to be recruited have had job descriptions checked by workforce to ensure consistency and speed up recruitment once SOC funding is in place.
A prior information notice was drafted during Q4 to notify the market a strategic advisor will be procured.
PBC endorsement has not been forthcoming as it is dependent on the clinical review.
Funding to deliver the SOC has not been forthcoming from WG.
A delegation from Cardiff University and C&V visited Edinburgh Bioquarter to understand their academic health science collaborations. This has provided C&V with further inspiration to build upon its Life Sciences vision with a workshop to take place in Q1.
WG confirm supplier to review clinical model in PBC is appointed
Prepare for SOC commencement
Supplier day held for strategic advisor procurement and tender for advisor written
Confirmation of SOC funding from WG
Commence recruitment to support SOFH programme (subject to funding)
Develop Life Sciences vision further with Cardiff University
Clinical delegation to visit Royal Liverpool
Undertake a series of reference meetings with NHP schemes to learn lessons
[Insert any additional documents here]
RISKS AND MITIGATIONS
RISK 1
Lost momentum after PBC not being endorsed
  MITIGATION
  Endorsement to be achieved after a clinical review. The ToR of this review are being drafted at the time of writing. SOC preparation can proceed.
RISK 2
There is a risk that all necessary funding for SOC is not available
  MITIGATION
  Executive colleagues will raise with WG
SEE SLIDE [13] IN BASELINE DOCUMENT

## Slide 20
SHAPING OUR FUTURE HOSPITALS
TARGET FOR LAST QUARTER
ACHIEVED TARGETS
TARGET FOR NEXT QUARTER
FURTHER READING
Complete SOC scoping after receiving feedback from WG stakeholders to ensure the right content will be produced.
Agree ToR with WG for clinical review of model presented in PBC.
With a stable SOC scope, build a costed delivery plan (including what expertise should be recruited and what should be procured)
Seek PBC endorsement and funding to deliver SOC from WG
  Commence any procurement and internal recruitment exercises once funding commitment has been received.
Adoption of Life Sciences Vision and actions
SOC scoping complete and agreement on it received from WG
ToR for clinical review agreed with WG. WG are procuring the supplier for CVUHB and Hywel Dda together.
Costed delivery plan complete and submitted to WG. Final costs will be reliant on tenders having been run.
Life Sciences Vision has been created. As a result of ever closer partnership working with Cardiff University, the strategy for the College of Biomedicine and Life Sciences is being recast, along with the future of Clinical Academics active in research. These will influence our life sciences vision so the document will remain open for amendments.
Detailed SOC planning to complete.
Receive feedback on SOC funding, commencing recruitment and procurement activity.
Participate in the WG commissioned clinical review providing all information they require.
Complete lessons learned report based upon reference contacts with New Hospital Programme schemes.
Plan and commence joint work with Cardiff University on how their College of Biomedicine and Life Sciences strategy will influence future operations and teaching.
Scope a Digital SOC which will inform/be informed by Shaping Our Future Clinical Services & Shaping Our Future Hospitals.
[Insert any additional documents here]
RISKS AND MITIGATIONS
RISKS
There is a risk that the time taken on the business case life cycle will see the UHB’s infrastructure deteriorate at an increased pace
MITIGATIONS
Endorsement to be achieved after a clinical review. WG agreed SOC preparation can proceed in the meantime. Funding request submitted.
Agreement to create high level SOC by WG.
Compliant procurement approach to any specialist advisors required using frameworks where possible
SEE SLIDE [13] IN BASELINE DOCUMENT

## Slide 21
OUR TERTIARY SERVICES STRATEGY
TARGET FOR LAST QUARTER
ACHIEVED TARGETS
TARGET FOR NEXT QUARTER
FURTHER READING
Submit South Wales Spinal Network (SWSN) business case / funding release for approval by WHSSC
Recruit and appoint network manager and team to the SWSN.
Submit funding releases for SWSN MSCC coordinators submitted for consideration through WHSSC CIAG process
Finalise clinical guidelines for Cauda Equina, MSCC and Spinal Trauma
Finalise MoU following review with legal and risk
Submit HPB option appraisal report to Project Board
Commence work on impact assessment and finance and commissioning appraisals
OG -Agree draft service model, engage with patients, carers and staff.
Plan and deliver 1st specialised services partnership workshop
Service specification for adult specialised endocrinology services approved in principle by NHS Wales Health Collaborative Executive Group.
Process for developing Specialised Infectious Disease Services service specification approved by NHS Wales Health Collaborative Executive Group.
South Wales Spinal Network team established – implementation project transferred from tertiary service team to SWSN to progress
Funding for SWSN MSCC coordinators confirmed and prioritised in WHSSC ICP
Benefit criteria and options by HPB Clinical Model Working Group
HPB service model option appraisal completed by External Advisory Group
Option Appraisal report quality assured by Clinical Model Working Group and approved by HPB Project Board.
1st specialised services partnership workshop held at Waterton Centre
Agreement to delegate commissioning responsibility for Sacral Nerve Stimulation to WHSSC
Agree future programme for specialised services partnership workshops
Plan and deliver 2nd and 3rd specialised services partnership workshop
Establish task and finish group to develop Specialised Infectious Diseases Services service specification
Plan and deliver workshop to develop implementation plan for adult specialised endocrinology
Agree reporting structure for RSSPPP with CEMT
Revise TSOG terms of reference and develop funding / commissioning proposal for PCD
Complete SAP workstream – present draft pathway and resource requirements to HPB Project Board
Commence HPB clinical impact assessment exercise
Agree and commence HPB patient engagement exercise
Agree principles for OG service model and commence engagement with patients, carers and staff
NB. All Spinal Network targets transferred to SWSN work plan.
RISKS AND MITIGATIONS
RISKS
Delay in agreement of definitive OG cancer service model for SBUHB
Delay in agreement on
MITIGATIONS
Continue to support SBUHB OG cancer service through outreach surgeon
SEE SLIDE [18] IN BASELINE DOCUMENT