| Priority area(s) to deliver 24/25: Increasing Enhanced Community Care (levels 3-4) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Key focus should be on delivering |  | Outcome focused, evidence-based community services through a place-based multi-professional working model of care. |  |  |
| Ref: | New - Increasing Enhanced Community Care (levels 3-4) |  |  |  |
| Resume of planning Milestones 23/24: |  |  |  |  |
|  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| Ref: | N/A | N/A | N/A | N/A |
| Progress synopsis |  |  |  |  |
| Outcomes of delivering Ministerial Priorities: |  |  |  |  |
| Ref: | - People seen right place first time (in the community where safe and appropriate) - Supporting people to remain at home - Reduced unnecessary hospital conveyance and/or admission |  |  |  |
| Planned Milestones 24/25 |  |  |  |  |
|  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| Ref: | Continued delivery of Phase 1 Safe@Home Establish learning from Phase 1 Safe@Home model. Planning to prepare to deliver Phase 2 Model. Robust data collection of baseline measure of Enhanced Community Care (levels 3-4). | Phase 2 Safe@Home model commences. Service redesign/realignment opportunities identified. | Progress wider service redesign/realignment of Enhanced Community Care services Implement increase to EoLcare capacity | Prepare to deliver increase in Community Nursing Services Progress Service redesign/realignment of Enhanced Community Care services Continue expansion of Phase 2 Safe@Home with increased capacity |
| Overarching outcome measures/ metrics: |  |  |  |  |
| Baseline position 23/24 | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
|  |  |  | Latest reported data: DN caseload 3,200, people seen 2,400 DN direct visits Weekday 14,100 Weekend 3,800 | Phase 1 implementation of Safe@Home Service. Capacity for 6 new referrals a day. |
| Performance Trajectories 24/25 |  |  |  |  |
|  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
|  | Enhanced Community Care – Safe@Home accept 6 new referrals per day To be confirmed in line with latest ECC request (10th Apr) Total referrals Total discharges Ave. LOS | Increase in number of patients supported through Safe@Home DN Weekend capacity on trajectory towards 60% of daytime capacity by 25/26. To be confirmed in line with latest ECC request (June): Referrals by source Discharge by destination Ave. ECC caseloads | Further increase in number of patients supported through Safe@Home Increase in number of patients who die in the community (planned) | Increased Safe@Home capacity (full capacity will provide caseload of 30 patients a day and around 174 patients per week) DN Weekend capacity on trajectory towards 60% of daytime capacity by 25/26. |
| Risks | Risks of Non-Delivery |  | Mitigations |  |
|  | Inability to recruit workforce to deliver Enhanced Community Care models Patient harm – Unnecessary hospital conveyance/admissions Not able to deliver the required care in the right place and at the right time |  | Assess services in scope of enhanced community care and identify options to realign service provision |  |
|  | Risks to Delivery |  | Mitigations |  |
|  | Funding allocation not realised to achieve full model delivery of Safe Home Phase 2- Continued unnecessary admissions/conveyances to EU/A&E |  | Robust performance monitoring and tracking of patient activity to demonstrate reduction in LoS/Bed days |  |
| Critical Enablers | Finance |  |  |  |
|  | - Reliant on Further faster funding allocations to deliver Enhanced Community Care. |  |  |  |
|  | Workforce |  |  |  |
|  | - Ability to recruit key workforce; Medical, Nursing, AHP staff will sufficient skills to meet enhanced community care needs of the population. - Service redesign and further integration of services to align capacity to system demands/needs, which may result in organisational change. - Development of multi-professional/multi-agency teams. |  |  |  |
|  | Digital |  |  |  |
|  | - Development of community systems and performance monitoring to robustly report on measures and demonstrate impact and value of enhanced care in the community. |  |  |  |
|  | Other (Specify) |  |  |  |
| Prevention & Population Health | Opportunities identified: |  |  |  |
|  | - Person centred, preventative, safe and effective services delivered though Community - Enable the population to live well and be supported at home when in need of enhanced care - Left shift focus of health board |  |  |  |