|  | Priority area(s) |
| --- | --- |
| Key focus should be on delivering | 52 weeks Outpatient Assessment and 104 weeks treatment recovery milestones to be achieved by 30 June 2023 and maintained throughout 2023/24 moving to 36 weeks RTT standards by March 2024. |
|  | UHB Aim: recover, reset and transform planned care, cancer and diagnostics services |
| Baseline | 10102 patients waiting >52 weeks for Outpatient 3740 patients waiting >104 weeks treatment by 31st March 2023. |
| Quarter 1: |  |
| - Milestones | KEY MILESTONES: - Approval of additional non-recurrent schemes and support for expansion of green zone UHL - Approval of regional cataract proposal - Predicted position for June 2023 cohort: <10,000 patients waiting longer than 52 weeks new outpatient <4,000 patients waiting longer than 104 weeks treatment |
| - Actions | - Submissions of planned to WG - Maintain weekly planned care performance meeting. - Track cohort reductions weekly at speciality level. - Deliver productivity and efficiency agenda through planned care programme - Focus on demand management and INNU - Monitor actual activity undertaken vs planned for outpatients and theatre treatments. - Approve capital work for UHL day surgery expansion |
| Quarter 2: |  |
| - Milestones | KEY MILESTONES: Predicted position (on basis that central non-recurrent funding is provided in May 2023): - <350 patients waiting >156 weeks for treatment - 0 patients waiting >156 for outpatients |
| - Actions | - Roll out of non-recurrent solutions following confirmation of funding - Maintain weekly planned care performance meeting. - Track cohort reductions weekly at speciality level. - Deliver productivity and efficiency agenda through planned care programme - Focus on demand management and INNU - Monitor actual activity undertaken vs planned for outpatients and theatre treatments. |
| Quarter 3: |  |
| - Milestones | KEY MILESTONES: Predicted position (on basis that non-recurrent and recurrent funding provided in May 2023): - <3788 patients waiting than longer than 104 weeks treatment |
| - Actions | - Continued delivery of non-recurrent plans - Go-live with additional UHL green zone capacity - Maintain weekly planned care performance meeting. - Track cohort reductions weekly at speciality level. - Deliver productivity and efficiency agenda through planned care programme - Focus on demand management and INNU - Monitor actual activity undertaken vs planned for outpatients and theatre treatments. - Undertake demand/capacity review for 24/25. |
| Quarter4: |  |
| - Milestones | KEY MILESTONES: Predicted position at March 2024 (on basis that non-recurrent and recurrent funding provided in May 2023): - 1263 patients > 104 week waits treatment - <9000 patients > 52 weeks new outpatients |
| - Actions | - Increase in activity in UHL green zone - Maintain weekly planned care performance meeting. - Track cohort reductions weekly at speciality level. - Deliver productivity and efficiency agenda through planned care programme - Focus on demand management and INNU - Monitor actual activity undertaken vs planned for outpatients and theatre treatments. - Review critical gaps to achieve future years targets and move towards 36-week monitoring |
| Risks | Underlying financial position Demand increase > available capacity Workforce availability Industrial action Issues are contained within a small number of extremely challenged specialities |
| Outcomes | Reduced overall waiting times for patients to be reviewed in outpatients. Reduced overall waiting times for patients to be treated. Improved patient experience. Reduction in overall volume of patients on an open RTT clock. |
| Alignment with workforce plans | Focus on priority areas: diagnostics (radiology, endoscopy, pathology) and theatres as critical enablers |
| Alignment with Financial plans | Speciality specific workforce plans to be included in individual Clinical Board IMTPs highlighting areas of risk Focus on priority areas: diagnostics (radiology, endoscopy, pathology) and theatres as critical enablers |