Completed by Cwm Taf Health Board as Hosts of the Regional Programme

|  | Priority area(s) |
| --- | --- |
| Key focus should be on delivering | Implement regional diagnostic hubs, to reduce secondary care waiting times and meet waiting time ambition in spring 2024 |
|  | UHB Aim: Ensure that regional working is embedding within the organisation and opportunities to improve care, reduce waiting times and deliver efficiency are maximised. |
| Baseline | Performance (Cardiff) - 4700 patients waiting > 8 weeks on a diagnostic pathway at the end of March 2023. Diagnostic programme: During 2022-2023, the SE Wales regional collaborative progressed joint planning to improve services in a number of key pressure and priority areas, including ophthalmic, orthopaedic and diagnostic services. The Diagnostics Programme has been established with project boards for: - Radiology solutions - Community Diagnostics Centres - Endoscopy, and - Pathology. A regional workshop on 28th November 2022 provided a re-set for the portfolio and delivered confirmed aims and objectives for each of the projects within the diagnostics programme. Milestones for delivery by April 2023 are: Community Diagnostic Centres: - Delivery of a position paper and investment rationale for the development of CDCs in SE Wales. - Updating the procurement specification to enable procurement to commence in 2023. - We have gained clinical consensus that all developments must fulfil the following criteria. - Delivery is more accessible to residents living in areas of deprivation and able to deliver to more than one health board population in the region - Developments deliver an increase in capacity - Developments will be founded on seeking sustainable solutions to demand backlogs. Endoscopy - Agreed revised project structure and governance arrangements with links to the National Endoscopy Programme. - Demand and capacity analysis completed with the support of the delivery unit. - Confirmation of process to be undertaken to develop an agreed model for regional endoscopy. - Cellular Pathology - Collection and agreement of Cellular Pathology Demand & Capacity Data - Progression of 7-day Cellular Pathology Working Pilot at CVUHB - Establish Regional Pathology Scoping Group - Develop and agree ToR Regional Pathology Scoping Group - Develop and agree Pathology Education Practitioner Roles - Scoping work to Identify and agree key interdependencies, constraints and possible options for regional working for short, medium and long term - Identify and agree short list of options for regional cellular pathology |
| Quarter 1: |  |
| - Milestones | - CDC – - Undertake capacity and demand modelling for the region - Option appraisal for scope, configuration of CDCs across the region, phasing and delivery options (both utilising internal solutions and procurement of external providers) - Preferred model and option selection and approval by Programme Board and Portfolio Oversight Board. - Completion of procurement specification - Completion of business case - Endoscopy - Confirmed model for endoscopy regional facility and which services lend themselves to regional provision, aligned to the intentions of the National Strategy - Feasibility study for potential sites to be undertaken. - Pathology - Advertise and recruit into newly developed training roles - Implementation of 7 day working at CVUHB for cellular pathology - Identify preferred option for regional cellular pathology |
| - Actions | - CDC: - Development of regional NHS options - Develop procurement strategy for the CDCs - Develop RFQs - Issue RFQ to potential suppliers - Endoscopy - ToR reframed to align with National Endoscopy Programme and Regional Diagnostics programme - Model task and finish group established - D&C assessment to be refreshed with options for development and at a procedure level - Assess operational requirements of the regional model including Academy requirements - Workforce requirements - Consider standardisation of job descriptions - Infrastructure - JAG accreditation requirements - Pathology - Site visit to Cardiff Edge - Further develop short listed options for regional pathology solutions - Develop operational requirements for identified options - Option appraisal of shortlisted options - Identification of available capacity due to implementation of seven day working model at CVUHB |
| Quarter 2: |  |
| - Milestones | - CDC: - Tender for CDC to be initiated and supplier selection completed. - Plan confirmed for staggered delivery of CDCs taking into account opportunities for sites in the region. - Endoscopy - Development of the business case for the regional model - Site option appraisal - Pathology - Agree preferred option - Produce model and service specification for preferred model - Movement of work across health board boundaries. |
| - Actions | - CDC - Confirmed supplier for procurement option - Pathways confirmed - Operational issues identified and solutions confirmed. - Endoscopy - Develop the business case for the agreed elements of regional endoscopy centre. - Pathology - Scope operational pathway of preferred option - Identification of operational requirements of preferred option - Develop regional training solutions |
| Quarter 3: |  |
| - Milestones | - CDC: - Implementation project to commence with NHS and/or preferred procured supplier option - Endoscopy - Seek approval of regional model and business case - Confirm action plan for JAG accreditation across the region, including the need for additional business cases as required - 4 endoscopy theatres (2 additional) at the Royal Gwent Hospital to be operational - Completion of 2 x additional endoscopy theatres at UHL - Pathology - Seek approval of regional model and agree funding stream - Implement regional training solution Performance (Cardiff) - 90% of diagnostic patients wait less than 8 weeks (excluding endoscopy) |
| - Actions | Regional diagnostics: - CDC: - Delivery actions to be undertaken including site development and equipment - Endoscopy - Development of a business case for the regional model for Endoscopy (8 Theatres and 2 Training Centres) - Options appraisal and feasibility study - Pathology - Development of business case for agreed regional model |
| Quarter4: |  |
| - Milestones | - CDC: - Infrastructure installed at 1st CDC - First CDC (Site TBC) fully operational - Potential Enabling/commissioning work for internal capacity options - Take opportunity to drive down waiting times for 8-week diagnostics so that over 90% of patients are within target - Endoscopy - Seek partnership ratification for the regional model and approval for business case to build endoscopy centre into 2024-25 planning cycle - Development of additional endoscopy theatre at Prince Charles Hospital. - Endoscopy Performance (Cardiff) - urgent <6 weeks; SCP <14 days; 0 surveillance patients 100% past target date - Pathology - Approval of business case |
| - Actions | - CDC: - Identification of further CDCs - Endoscopy - Business case will be progressed through programme and regional portfolio governance structures - Pathology - Business case will be progressed through programme and regional portfolio governance structures |
| Risks | Regional diagnostics: - General - IT systems can’t share information across HB boundaries and that patient records get lost through manual processes. Mitigation additional IT support into the programme to provide expertise - CDC: - Approval by all 3HBs of the Business Case is not achieved. Mitigation is a robust Business Case - Service provider unable to fulfil staffing requirements. Mitigation Good contract management and open communication with the Service provider - Necessary Funding for the programme is reduced or not available. Mitigation robust Business Case demonstrating the financial value as well as improved patient care - Endoscopy - Approval of the model and business cases is not achieved for all 3 HBs. Mitigation – robust engagement mechanisms and business case. - Pathology - Delivery of the LINC system |
| Outcomes | Radiology - CDCs The Outcome of this project would be a delivery model consisting of a 3 stage process: - Diagnose Well - - Rapid access to the right diagnostic - Increase accessibility - Rapid availability of diagnostic outcomes - Manage Well - - Develop pathways where diagnostics before referral are the norm - Access for planned and emergency care pathways in the community to ensure that management is always as close to home as possible - Virtual links to primary care to aide decision making where a referral is not required - Live Well - - Develop clear plans for patients that do not have a clear diagnostic outcome - Support primary care with pathways of management for the "worried Well" - Links to therapeutic interventions In so doing we will ensure: - We deliver a high standard of care as defined by the Health Boards and by national and international best practice guidelines. - CDCs are sufficiently resourced to ensure access. - Services are accessible to patients, are appropriate to their needs and responsive to their concerns. - Employ continuous, transparent, quality assurance as the main method of maintaining and improving standards of care. - Demonstrate improvements in process and outcomes, year by year. - Provide a seamless service from the point of referral. - Ensure people with disabilities, additional needs and languages other than English or Welsh are able to use the service. - Identify and implement regional pathology solutions to create a robust, sustainable, future proofed and patient focussed service. |
| Alignment with workforce plans | Radiology: The project will include both development work for NHS based and procured solutions, with a view to the development of the workforce to transition from procured to NHS delivered services in the longer-term. There will be a contractual requirement within the procurement for any provider to work with NHS wales to not destabilise our current workforce and to support in alternative workforce models. This requires alignment of demand and capacity modelling and service development with workforce planning, including commissioning training places. Endoscopy Amongst the constraints to the optimisation of current endoscopy services is recruitment and retention of sufficient workforce. The development of the training academy as part of a regional solution would support an enhanced pace of development of endoscopist roles to be able to deliver the required capacity for the region. |
| Alignment with Financial plans | All funding decisions for the regional portfolio are undertaken at the portfolio oversight board, at which the three Chief Executive Officers are represented. Health Boards have given consideration to the requirements for diagnostics funding within their plans for 2023-24 as part of wider planned care recovery development work. The proposals for CDCs will include both internal and procured solutions, with the intention that the procurement service specification facilitates a flexible approach to accessing CDCs to meet the needs and capabilities of the region. On behalf of the region, Cardiff and Vale UHB has commissioned work from Cardiff University (Cedar) to support the value assessment, health economics review and a social return on investment completed in order to ensure that the outputs drive improved outcomes for patients at a lower cost for overall health care provision. |
| OPTIONAL |  |
| Digital / Technology Opportunities | Pathology Procurement and Implementation of Digital Cellular Pathology enablement is key to the success of any regional pathology solution – Digital Cellular Pathology Business Case |