|  | Priority area(s) |
| --- | --- |
| Key focus should be on delivering | Implementation of fully functioning “same day emergency care” service for both Medical and Surgical patients. |
|  | Honour commitments to deliver improvement of 25% for total lost hours per week and average lost minutes per arrival for ambulance handovers. |
|  | UHB Aim: enable people with urgent or emergency care needs to access safe and high-quality care at the right time, in the right place. |
| Baseline | Ambulance Handovers Oct 21: 25% reduction of lost minutes per ambulance arrival (36 mins) Eliminate 4-hour ambulance delays Jan 23 Lost hours due to handover delays – 338 hours per week Lost minutes per ambulance arrival – 34 minutes SDEC 4090 patients through SDEC in Q3 2022/24 |
| Quarter 1: |  |
| - Milestones | - Increase virtual ward activity by 20% in both surgery and medicine SDEC - Maintain zero 4-hour ambulance delays - Direct access from WAST to Medical SDEC - Zero 24 hour waits in EU - Increase SDEC attendances to > 5000 per quarter |
| - Actions | - Implement consultant connect across medical SDEC - Redesign assessment units moving to alternative environment and further developing clinical pathways - Develop cohesive medical workforce plan for key specialist services in medicine and specialist to include Gastro / Neuro / Repository/ General Medicine - Agree location and introduction of Diagnostic Day Unit - Explore integration of surgical and medical SDEC |
| Quarter 2: |  |
| - Milestones | - Introduce four bedded gynaecology same day emergency care unit - Reduce ambulance handover average lost minutes to 30 minutes. - Reduce 12-hour ED waits by 50% of Jan ’23 baseline - Reduced number of unplanned re-presentations within 7-days of SDEC attendance - Convert current trauma SDEC pilot in to long term sustainable SDEC |
| - Actions | - First two non-surgical specialities introduce revised week on-call rota. (Including consultant connect) - Establish clinical decision unit in EU footprint UHW. - Establish four bedded gynaecology SDEC - Development of cluster and MDT work to compliment UPC and upstream working to support WAST conveyancing reduction Tier 1 Emergency Unit - Define trauma SDEC model and confirm long term location |
| Quarter 3: |  |
| - Milestones | - Reduction ED majors’ attendances by 5% - Maintain ambulance handover average lost minutes to 30 minutes - Improve % of take managed in SDEC without requiring admission |
| - Actions | - Four specialities running week on-call rota within medical and specialist services (TBC) - Re-establish acute response team to reflect patient demand with ID consultants - Introduce CRT & VCRS hub in UHW with redirection of patients with social flags away from acute inpatient setting - Agree frailty bed base model with corresponding outreach service - Plan to consolidate acute gastro in UHW - Increase SDEC attendances to >6000 per quarter |
| Quarter4: |  |
| - Milestones | - Increase SDEC attendances to >6500 per quarter - Maintain ambulance handover average lost minutes to 30 minutes |
| - Actions | - All medicine specialities running week on-call rota within medical and specialist services (Consultant connect) (TBC) - MDT across every locality aligned to high-risk patients and “health days” - Job planning for emergency rotas completed - Revised clinical pathways written for MDT - Information sharing between partners (governance issues resolved) to capture high-risk cohort and maintain |
| Risks | - Workforce constraints, medical model of care to move towards week rota for all - Transitional funding to support secondary to primary resource shift - Engagement with partnership organisations |
| Outcomes | - Reduction in emergency inpatient stay (TBC) - Decrease in readmission rate - Decrease in WAST conveyances - Deliver ambulance handover standards as per WG - Increase “Health Days” - Decreased mortality and morbidity - Increased direct access to SDEC from WAST |
| Alignment with workforce plans | - All plans align to: redesign of clinical roles and responsibilities, value for money and working at top of licence, non-registrant clinical roles - Reduction in premium workforce costs impacting on quality of care - Redeployment of resource to increase community services along with reduction in inpatient footprint - Reduction in locum and WLI payments - Strengthen quality measures supported evidence-based planning and outcome-based delivery |
| Alignment with Financial plans | - Reduction in inpatient bed footprint - Reduction in premium workforce costs - Quality improvements leading to cost reduction and value-based services. - £2.9m six goals is allocated across priority schemes in SDEC, CAV 24/7 and Urgent Primary Care, and programme support. Further detail is being provided to the Six Goals programme. |