## Slide 1: Theatre Review Project 2025/2026 Improvement Plan Approach & Design
Project Team
23 May 2025
Susan Hostler 23 May 2025

## Slide 2: What is a Tranche Approach?
A tranche is a defined segment or batch of work, often grouped
by either time, theme, or priority. It allows you to:
  Focus on manageable chunks
  Review and adjust between tranches
  Rigorous governance
  Align with funding/resource availability
  Allows for learning and reflection

## Slide 3: Tranche Criteria – Priority based approach
Tranche ID | Priority level | Priority Description | Themes | Actions (from report) | Timescales (April 2025 –April 2026)
T0 | All | Foundation actions for proceeding Tranches. Quick wins/easy to do. Aim, to improve staff engagement. |  |  | Now
T1 | Critical / Immediate | Critical actions which have high impact Enablers for Tranche 2. |  |  | Quarter 2 2025 (In progress)
T2 | High | High, very important actions. Dependant on T1 (less time critical). Enablers for Tranche 3. |  |  | Quarter 3 2025
T3 | Medium | Valuable actions but not as time sensitive. Dependant on T2(less time critical). Enabler for Tranche 4. |  |  | Quarter 4 2025/26
T4 | Maintenance/Monitoring | Transition phase to business as usual. Embedding, checking sustaining actions. Period of reflection and learning. |  |  | Quarter 1 2026

## Slide 4: Tranche Design and Governance
Tranche Design:
Agree scope for each tranche – actions. (Planning session 10th June)
Identify the dependencies between actions.
Develop resource plan for each Tranche.
Each report action will be allocated a tranche and has an owner, start/ end dates. dependencies/constraints and performance measures.
Planning for the next tranche will start in the previous tranche.
Tranche Governance:
Fortnightly project board.
Weekly project meetings.
Risk and issue management.
Roles and responsibilities clearly defined.
Tranche check point reviews – provide assurance, ensure on track to deliver. Escalation/corrective action if off track.
Tranche close - down – did we deliver all actions? Can we proceed to next tranche?
What did we learn?
Benefits tracking.

## Slide 5: Theatre Review Project 2025/2026 Design Actions from report will be allocated to a Tranche based on priority– meeting plan 10th June.
Tranche 1
(Critical/Immediate actions)
Tranche 0
(Foundation Level & quick wins)
Tranche 3
(Medium actions)
Tranche 2
(High level actions )
Tranche 4
Transition Phase
Embedding/sustainability
For each Tranche:
Scope designed/agree
Tranche delivery
Plan next tranche
Fortnightly check point reviews
Decision to close/ proceed to next Tranche
Benefits tracking
Lessons learnt
Weekly Project Meeting
Fortnightly Project Board
SLB, SOFQE
Co-Production

## Slide 6: Tranche Zero at a glance:
ID | Action | Comment | Owner | Completion date
01 | Set up weekly project session. | Meetings in place. | Sue Hostler | 19/05/2025
02 | Set up fortnightly project board. |  | Sue Hostler | 30/05/2025
03 | Send out a staff survey – 3 things that matter to me. | Survey to be sent on 27 May – staff to complete by 30 May | Chloe Chettleburgh | 30/05/2025
04 | Arrange staff engagement session. | Location to be agreed. | Nick Tyson | 09/06/2025
05 | Arrange Theatre Review Tranche planning session. | All day session planed for the 10 June with project team. | Sue Hostler | 22/05/2025
06 | Utilisation of Viva engage Surgery page. | Use platform to share information and progress. | Chloe Chettleburgh | 06/006/2025
07 | Formal and informal engagement sessions to provide progress update. |  |  | 09/06/2025
08 | Utilisation of Office 365 functionality for project management. | Project planning/tracking to be managed in office 365. | Nick Tyson | 30/05/2025
09 | Utilisation of AMT to provide reporting. |  | Matt McCarthy | 30/06/2025

## Slide 7: Tranche one at a glance:
ID | Theme | Description | Owner
1H | Values and Behaviours | Explore security options to make the female changing area a more secure place to leave belongings | Paul Warman
8A | Patient and Staff Safety and Experience | Audit adherence to policies and procedures for consent and ‘WHO Checklist’, ensure standardised application across all theatres and provide update training as required. | Who Collaborative
8B | Patient and Staff Safety and Experience | Examine the management of paediatric cases operated on in Mains Upper and determine whether the current arrangement of recovery in the adult recovery area aligns with the Royal College of Anaesthetists' Guidelines (Chapter 10: Guidelines for Provision of Paediatric Anaesthesia Services 2025). Assess the measures taken to safely manage children. Investigate what is required to fully utilise Children's Hospital for Wales to ensure that paediatric cases are operated on and recovered within Children’s Hospital for Wales. | Simon Slinn, Rachel Whittle, Thomas Kitchen
8E | Patient and Staff Safety and Experience | Create standard operating procedures for the setup and standardisation of anaesthetic rooms throughout the department, where feasible. | Barbara Jones and Ruth Jones
8H | Patient and Staff Safety and Experience | Standard Operating Procedures and schedules for the theatre deep cleaning rota, including weekend protocols that are standardised across all theatre suites | Theatre Managers
8J | Patient and Staff Safety and Experience | Charitable bid to the Staff Lottery Fund to refurbish the staff room, including new furniture, fridges and a dishwasher | Paul Warman

## Slide 8: Next Steps
Produced a detailed Tranche 0 and Tranche 1 Plan.
Weekly project meeting.
Staff survey – three things that matter to me.
Staff focus group.
Planning session.
Set up project board to agree Tranche zero and Tranche one scope and timescales for delivery.