Table 1:  Action List

| Team | Issue | Action | Lead |
| --- | --- | --- | --- |
| Paediatrics - Clinical | - Number of new patients below JACIE threshold of 5 p.a. - Only “first transplants” count to total. - Paediatric outcomes are excellent with 0% mortality. Therefore, closing the programme and referring patients to NHSE would result in a worse patient experience and potentially jeopardise outcomes. | - Keep paediatrics as part of SWBMT Programme - Would require sign-off by CVUHB and JCC - Paediatric team preparing document and will meet with KW | Cathy Morley-Jacob |
| Paediatrics - Collection | - Number of bone marrow harvests below JACIE threshold - Number of apheresis harvests insufficient to maintain competencies | - JACIE has suggested introducing simulation procedures or ceasing activity - Option to maintain apheresis competency by doing adult procedures - Meeting being arranged with KW to discuss options | Cathy Morley-Jacob Jim Murray |
| Paediatrics – Personnel | - Single nurse capable of performing apheresis procedures (succession planning needed) | - Consider paediatric nurses maintaining competencies on adult patients or alternatively adult nurses performing procedures on paediatric patients to improve robustness of cover | Cathy Morley-Jacob Jim Murray |
| Processing Facility – Personnel | - Insufficient staffing - Unable to provide on-call cover for LN2 storage tanks (also noted by HTA as a deficiency) | - CAR-T phase 2 business case with JCC since 06.2024 - To review staffing requirements and update BC as needed - KW meeting with JCC on 23.01.2026 to review JACIE report | Sian Jones Sarah Phillips Keith Wilson JCC |
| Processing Facility – Premises | - Inadequate for expanding needs (e.g. CAR-T). - Offsite storage being used as mitigation but recent SAE with loss of irreplaceable material – reported to HTA – investigation ongoing. | - Strategy needed at UHB level regarding cellular and advanced therapies: - Expand on UHW site - Move to alternative site - Joint venture with WBS | Estates Sian Jones Sarah Phillips Keith Wilson |
| CVUHB – Premises | - All adult premises woeful. Detailed strategy needed by deadline of 08.07.2026 for: - Inpatient facility on B4/C5 Haem - Ambulatory Care - Haem Day Centre (Adults) - Day Centre (TCT) - Outpatients (CVUHB) | - Upgrade of HDC Adults in progress - TCT-aged patients to use upgraded adult facilities until upgrade of TCT facilities - Review scope for addition of OPD to HDC upgrade - Ambulatory Care upgrade requires relocation of clinical offices - Ward upgrade only possible with new build | Estates Clinical team |
| SBUHB – Premises | - Expansion needed if increased throughput planned | - Review current maximum throughput and confirm impact on staffing | SBUHB finance Ann Benton Keith Wilson |
| SBUHB – Staffing | - Insufficient medical and staffing cover to meet JACIE standards - Over-reliance on single nurse specialist - Two-tier system: - Nurse-led roles recommended as per CVUHB - Patients do not benefit from prehab as at CVUHB | - Perform gap analysis of existing staffing and pathway requirements - SBUHB to write BC to adopt JACIE recommendations | SBUHB finance James Leaves Ann Benton Keith Wilson JCC |
| SWBMT Team | - Correction of partial and non-compliance | - Quality team to meet with relevant sections to update paperwork - SSCB to fast-track approval of replacement Band 4 Quality Officer - SSCB to fast-track approval of Band 7 Quality Manager maternity leave | - Quality team headed by Nicola Davies - Jess Castle for SSCB |

Table 2: SWBMT Programme compliance as assessed by JACIE Inspectorate

| Section | Compliant | Partially Compliant | Non- Compliant | Not applicable | Total |
| --- | --- | --- | --- | --- | --- |
| Part B: Clinical -UHW Adult + IEC Auto | 226 | 23 | 23 | 01 | 273 |
| Part B: Clinical -Paediatrics (Only Auto) | 172 | 57 | 06 | 39 | 274 |
| Part B: Singleton (Auto Only) | 204 | 16 | 09 | 45 | 274 |
| Part B Clinical QM Adult+Paed | 127 | 05 | 02 | -- | 134 |
| Part B Clinical QM Singleton | 119 | 06 | 02 | 03 | 130 |
| Part CM BM Adult + Paed | 89 | 20 | 06 | 07 | 122 |
| Part CM QM Adult + Paed | 25 | 05 | --- | 04 | 34 |
| Part C Apheresis PAED | 120 | 35 | 14 | 10 | 179 |
| Part C Apheresis Adult | 152 | 19 | 05 | 05 | 181 |
| Part C Apheresis QM Adult+Paed | 102 | 05 | 04 | 02 | 113 |
| Part B-CM-C Donors | 101 | -- | -- | -- | 101 |
| Part D Processing | 206 | 56 | 14 | 11 | 287 |
| Part D Processing QM | 118 | 04 | 01 | -- | 123 |
| Labels - Collection | 14 | 02 | -- | -- | 16 |
| Labels- Processing | 61 | 05 | 3 | -- | 69 |
| Labels- Shipping and Transport | 18 | 02 | --- | --- | 20 |
| Total | 1854 | 260 | 89 | 127 | 2330 |