Minutes of the Shaping Our Future Hospitals Committee

Held On 21st July 2021 at 9:00am

Via MS Teams

| Chair: |  |  |
| --- | --- | --- |
| Rhian Thomas | RT | Independent Member – Capital & Estates / Committee Chair |
| Present: |  |  |
| Abigail Harris | AH | Executive Director of Strategic Planning |
| Catherine Phillips | CP | Executive Director of Finance |
| David Edwards | DE | Independent Member – ICT |
| Edward Hunt | EH | Programme Director - Redevelopment |
| Gary Baxter | GB | Independent Member – University |
| Nicola Foreman | NF | Director of Corporate Governance |
| Stuart Walker | SW | Executive Medical Director. |
| Secretariat |  |  |
| Raj Khan | RK | Corporate Governance Officer |
| Apologies: |  |  |
| Charles Janczewski | CJ | UHB Chair |
| Len Richards | LR | Chief Executive Officer |

| Item No | Agenda Item | Action |
| --- | --- | --- |
| SOFH 21/07/001 | Welcome & Introduction The Committee Chair (CC) welcomed everybody to the meeting |  |
| SOFH 21/07/002 | Apologies for Absence Apologies for Absence we noted. |  |
| SOFH 21/07/003 | Declarations of Interest Independent Member – University declared an interest of being employed by Cardiff University who are a partner and stakeholder in SOFH |  |
| SOFH 21/07/004 | Stakeholder Engagement updates The Executive Director of Strategic Planning (EDSP) advised the committee that the Programme Business Case (PBC) had been completed in record time and had been delivered in the timeframe that was required. It was noted that about one month had been lost due to procurement and the time that had taken to finalise. The EDSP advised the committee that since the submission to Welsh Government (WG) in March 2021, the Gateway review had taken place. It was noted that in relation to Stakeholder engagement, the project was not just important to Cardiff and Vale University Health Board (CVUHB), but to multiple partners and stakeholders as well as WG. For clarity, it was noted that 85% of activity at the University Hospital of Wales (UHW) is Cardiff and the Vale activity. It was noted that to keep stakeholders engaged, the EDSP, the CEO, the Executive Medical Director (EMD) and the Programme Director – Redevelopment (PDR) had met with partnership organisations and all partners had sent endorsement letters. It was noted that some important points had been considered which included: - Cardiff University showing strong support and indicating intent to invest £200m - £300m in Health Park West - c£17m to date in purchasing the land and c£3m more over the coming year - Cardiff Council eye a large regeneration opportunity - Wide Welsh Government participation in our Gateway 0 review - Key messages over next period to the NHS family in South Wales - Case for change is strong - Awaiting WG scrutiny outcome - Not predetermined any shape/form/location of scheme - Looking forward to working together on service planning and life sciences - Search for new allies within Cardiff & Vale of Glamorgan who are aware of our strategy? - Publication of a brochure/prospectus It was noted that it presented the opportunity for UHW to be the anchor institution for economic growth in Wales. Not just about providing wards and bed and a new A&E department, it was so much more than that. The EDSP advised the committee that she and the PDR had met with Cardiff University as they had recently purchased the land next door to UHW and now had possession of that. Cardiff Council see itself as a leading city from a European context and also a UK context. Real regeneration opportunities linked to this development. It was noted that in the endorsement letter from Cardiff Council they had said that the redevelopment of the hospital would be the biggest economic regeneration offer that would happen in the City. The EDSP highlighted that they met with Cardiff University and it was noted that the Programme Business Case was a really good and thorough document and an excellent piece of work but felt it would be useful to produce a prospectus for Cardiff University to articulate the benefits for this. IM-U reiterated that WG had not handled an investment of such scale before and asked if any approvals beyond WG would be required, for example, Whitehall? The Executive Director Finance (EDF) responded that they were unsure at this stage and that it all depended on the funding route. She stated that if it’s something WG can manage with a consortium of partners and different funding sources, then it can be held in Wales. If they’re relying additional support that requires treasury approval then that would require further scrutiny and approvals outside of Wales. The CC noted that the EDSP had mentioned that it was not just a health and social care issue as this would affect a number of different portfolios of work and asked if there was a plan for that or is there an assumption that Health & Social care representatives would be doing the advocating work for them. The EDSP responded that in terms of stakeholders they would work with the Health & Social care representatives during the preparatory work but most importantly was the scope of the PBC was agreed with them. She stated that they took it upon themselves to ensure they held discussions with key officials: - Simon Brindle – The Director, Covid Recovery and Restart reconstruction. - Simon Jones – The Director of Economic Infrastructure. - Department of Health & Social Services and finance colleagues. The Shaping Our Future Hospitals Committee resolved: a) During the pre-PBC endorsement period, Seek to increase the level of advocacy for the programme amongst stakeholders |  |
| SOFH 21/07/005 | Welsh Government meeting outcomes. The PDR advised the committee that a meeting had been held with WG on 22/6/21 to have the first opportunity to discuss their thoughts on the SOFH PBC. It was noted that it had been attended by key NHS Wales executives led by Andrew Goodall, plus most of the executive team from C&V, the VC of Cardiff University, Chief Exec of Cardiff Council and MD of WHSSC. The PDR noted that Andrew Goodall, the Chief Executive NHS Wales (CENW) had said the CVUHB had achieved a lot and were on a good trajectory and were exemplars in many different areas. It was recognised by the CENW that doing nothing would not be an option and would involve spending significant amounts of money and that the new minister was aware of the PBC where conversations were also had with the new minister discussing that investment at this scale would be required. It was noted that WG had stated that currently there was no governance in place for a project of this size. The CENW had asked the PDR, the EDSP and the Director of Capital, Estates and Facilities (DCEF) for an action to explain what the next 10 years could look like from the CVUHB perspective and that without a line of sight to a new UHW there are significant issues and what they are such as: - Backlog maintenance - Blocked pipes - Aged electrical distribution boards The PDR added that they also need to consider the areas where they are also deficient in such as: - Bone Marrow transplantation - Critical Care The PDR highlighted that their wards are not HBN compliant and an exercise was done to see that if the wards were brought up to compliance then a 38 bed ward would become a 19 bed ward. Since the meeting CVUHB have had a note back from WG post scrutiny feedback which included: - Whilst the PBC went into more detail than they expected, the scrutiny has asked for a copious amount of detail on the implications of the CVUHB clinical model and draw that out into a more thorough options appraisal. - WG also wanted a more thorough economic analysis - WG want them to go in and quantify what the transformation opportunity was. It was noted that the EDSP and the PDR would prepare a response and have a meeting with WG urgently. The CC stated that she had found it challenging that a scope had been agreed at the beginning of the year which was delivered to and then there is now an alternative perspective provided post submission of the PBC. She asked what could be done to avoid duplication of work and that path and ensure delivery of what is exactly needed. The EDSP responded that it has to be a partnership with WG and CVUHB as they fundamentally know that UHW is coming to the end of its life and that doing nothing is not an option and would require significant funding if they continually repair it. She stated that they would need to regularly go back and test their assumptions with Welsh Government and ensure they keep an open dialogue. IM-U queried if there is a clear sense of what WG officials are doing now and whether they are committing a team to working on this project? The EDSP stated that this is the question they need to be asking and that the desire for the PDR and herself is to meet with key officials is really important as within the gateway review this is an action that needs to be done in a particular timeline. She highlighted that there will be different views from different officials and that WG would all need to understand the PBC and provide their definitive overall view on it rather than taking views of multiple government officials. The Shaping Our Future Hospitals Committee resolved: a) Note the meeting notes and actions. |  |
| SOFH 21/07/006 | JLL Report The PDR advised the committee that as part of the consortium that Grant Thornton bid around Christmas time, there were various other partners brought on board with various types of specialisms such as property and health planning. He stated that they were motivated by the investment that Cardiff University were making in Heath Park West predominantly. We felt it was courteous to give Cardiff University a view if likely they would stay at UHW or if other options exist. The PDR advised the committee that they had commissioned a small independent piece of work to understand were 22 hectare sites existing in Cardiff JLL undertook that work and list of around 25 sites which was shocking in Cardiff and the Vale. It was noted that when simple criteria was applied, the numbers rapidly diminished. The PDR stated that there are 3 options: - Current UHW site - Associated British Ports owned Cardiff Bay Site - Culverhouse Cross Site. It was noted that the Culverhouse Cross site would most likely be pushed out due to economical regeneration opportunity that existed there. It was highlighted that Cardiff Council were excited about the development on the original UHW site but when they saw the opportunity for Cardiff Bay further interest was generated as they saw an enormous regeneration opportunity on the site on top of what was already seen. He added that they had perceived an investment in the current Heath site as a stimulus of the life sciences industry whereas Cardiff Council would perceive the opportunity in doing that but also stimulating investment in things such as housing and further regeneration. The PDR informed the committee that Cardiff Council have agreed to undertake a small piece of work to further understand what the regeneration opportunity of the area would be. The Shaping Our Future Hospitals Committee resolved: a) Note the content of the report and that further site search work will be undertaken in subsequent stages |  |
| SOFH 21/07/007 | Gateway 0 Report The PDR advised the committee that a Gateway 0 review was held between 21/06/2021 and 23/06/2021. The outcome of the review had been provided as a paper to this committee along with the final SRO response. The PDR highlighted that when they received the results of the review in regards to the delivery confidence assessment they received an amber/red status. This meant that successful delivery of the programme was in doubt with major risks or issues apparent in a number of key areas which came as a surprise to the PDR and EDSP. He stated that the findings were based largely on affordability but also some other factors that were raised that also needed to be addressed such as: - Difficulties in regional health planning - Ownership and participation from WG The PDR highlighted that during his interview he was asked about conversations had with WG and it was noted that WG had proposed a higher sum of monies than what the Health board had discussed since the start of their conversations which began in 2019. The PDR stated that the recommendations suggested help push WG towards a mandate and that they were asked to strengthen their case for change at UHW as they would like to see more work in regards to the digital strategy. He highlighted that they were also asked to go through the further options appraisal with the long and shortlisting, which he felt should be undertaken at a strategic outline case stage rather than being undertaken now. The PDR highlighted that there were further suggestions around the wider governance on bringing in partners particularly around academic health sciences as the stakeholders involved are quite broad and influential i.e. department of trade, council, university. The PDR stated that the recommendations were helpful as it highlighted work that they want to do but are things they wish to do at a strategic outline stage as opposed to a business outline case. In terms of implications for work that needs to be completed he stated that it points to what is referred as project 1 in the programme business case meaning that they need to proceed with the clinical transformation and the associated digital implications of that. The PDR informed the committee that although work is being done with some of the projects what is not available is the cost implications of the works and also informed the committee in regards to governance the Academic Health Sciences feasibility work would also need to be undertaken. The PDR stated that they would be writing back to WG and meet with them from which they would be able to take their points from the letter, the Gateway 0 recommendations and have more robust conversations with WG to discuss when the best time would be to undertake this in the next stage. The EDF highlighted to the committee in regards to the funding, affordability, and the request for the “do nothing” option. She stated that what is being suggested is that on one hand a figure has been presented and on the other there is another large figure which they must deal with and will have a sub optimal outcome if “x” amount is spent. The EDF stated that they must be pragmatic in their approach and consider the quality of their costing in the original £2 Billion. The CC queried if considerations have been made to determine things that do not need to be updated/renewed. The PDR responded that the programme business case did consider the do nothing / do minimum options but they did not work it through as it would leave potential grey areas between replacements and do minimums. He stated that this is done at strategic outline stage. The CC asked to change the recommendations on the report and confirmed a new recommendation. The Shaping Our Future Hospitals Committee resolved: - Acknowledge the recommendations made in the report - Note that further discussion will be held with Welsh Government to agree implementation of recommendations to achieve endorsement of the PBC. |  |
| SOFH 21/07/008 | Programme Overview No Further points were raised The Shaping Our Future Hospitals Committee resolved: - Note the position of the programme and the intent to seek WG endorsement of the PBC as soon as practical to allow progress to be made on our three identified projects. |  |
| SOFH 21/07/009 | Risk Register / Risk Overview The PDR stated that they have already discussed the current issues in progressing the business case and the risks identified around unintentional delays between stages were captured in the original risk register that was submitted with the programme business case. He informed the committee that they were not spending as a result of these delays by having to maintain teams that are potentially not in use He highlighted that funding would always be a risk due to the value and the options being quite complex. The EDSP highlighted when considering to proceed with the development of the programme business case, one of the areas that they had concerns about was the engagement with the clinical frontline. She informed the committee that they received an unexpected and overwhelming amount of responses back with hundreds of clinicians attending the workshops. The EDSP stated that she perceived a buoying of the workforce being able to influence change. The DCG informed the committee that discussions were already held with the PDR in regards to the format of the register to ensure there is some consistency within the organisation and to avoid different styles being introduced. The DCG stated that the committee oversees and scrutinises the work of the programme board so it would be better to see the top level risks rather than all the risks so that way they are sighted on them to be able to provide assurance to the board. The Shaping Our Future Hospitals Committee resolved: - Note the risks - Amend any existing risks - Add any new risks |  |
| SOFH 21/07/010 | Shaping Our Future Hospitals Committee – Terms of Reference The DCG informed the committee that the Terms of reference was taken to the Board meeting in May and highlighted that going forward this will need to be under constant review and development. The Shaping Our Future Hospitals Committee resolved: - Review and Note the Terms of Reference as set out |  |
| SOFH 21/07/011 | Annual Workplan 21-22 – Shaping Our Future Hospitals Committee The DCG stated that this need to remain a fluid document at the moment as the role of the committee is to have oversight and scrutiny of the programme boards work and at the moment will take them through the programme business case, strategic outline case, outline business case, and the final business case and holding the programme board to account on delivery of those business cases to provide assurance to the board. The Shaping Our Future Hospitals Committee resolved: - Review and Approve the Committee Work Plan for 2021/22 - Recommend Approval to the Board on 30th September 2021 |  |
| SOFH 21/07/013 | AOB No other business was noted. |  |
| SOFH 21/07/014 | Review of meeting The CC asked if attendees were satisfied with the business discussions and format of the meeting, and alI Committee members confirmed it was a positive meeting with an appropriate level of Independent Member challenge and scrutiny. |  |
| SOFH 21/07/015 | Date & time of next Meeting October 13th 2021 at 9am via MS Teams |  |